ONX CIVILIZATION SYSTEMS

Gate 7

Preparation Package

Provisional Planning Document — Not Yet Authorized for Execution

Doc ID: ONX-G7PP-2026-001

Authority: L1 — Founder Constitutional

Date: 2026-06-18

Status: PROVISIONAL — All elements subject to change until Gate 6 closure

# 1. Gate 7 Mission Hypothesis [PROVISIONAL]

[PROVISIONAL] If Gate 6 successfully deploys multi-agent AI and conversational interfaces, then Gate 7 should focus on deepening the civilization's self-awareness through advanced analytics, civilization health monitoring, and intelligent operational insights. Gate 7 transforms ONX from a reactive Q&A system into a self-monitoring civilization with proactive intelligence.

## 1.1 Guiding Hypothesis

[PROVISIONAL] The ONX Civilization will demonstrate maturity when it can measure its own operational health, identify knowledge gaps autonomously, and suggest improvements to its own architecture — without Founder intervention.

## 1.2 Why Gate 7 Matters

•  Gate 5 established presence. Gate 6 establishes intelligence. Gate 7 establishes self-awareness.

•  Analytics provide the feedback loop that makes continuous improvement possible.

•  Without Gate 7, Gates 8-10 (community, integrations, launch) operate blindly.

# 2. Gate 7 Objectives [PROVISIONAL]

1. [CANDIDATE] Deploy comprehensive civilization analytics dashboard with real-time metrics, historical trends, and health indicators

2. [CANDIDATE] Implement autonomous knowledge gap detection — AI analyzes query patterns to identify unanswerable questions and suggest new corpus topics

3. [CANDIDATE] Build Titan performance scoring system — measure response quality, engagement, and knowledge coverage per Titan

4. [CANDIDATE] Create visitor journey analytics — track navigation paths, session depth, and engagement drop-off points

5. [CANDIDATE] Implement civilization health score — composite metric reflecting knowledge completeness, AI performance, visitor engagement, and system stability

6. [CANDIDATE] Ingest Corpus Batch 4 (~15-20 documents, topic TBD by Founder)

7. [CANDIDATE] Produce governance documentation for Gate 7 analytics framework and data privacy compliance

# 3. Expected Deliverables [CANDIDATE]

| ID | Deliverable | Type | Likelihood |
| --- | --- | --- | --- |
| 7.1 | Analytics Dashboard (/analytics) | New page + components | High |
| 7.2 | Knowledge Gap Detection Engine | AI service + UI indicator | High |
| 7.3 | Titan Performance Scoring | AI service + dashboard widget | High |
| 7.4 | Visitor Journey Tracking | Analytics service + visual flow | Medium |
| 7.5 | Civilization Health Score | Composite metric + display | High |
| 7.6 | Corpus Batch 4 Ingestion | P-01 pipeline execution | High (pending topic) |
| 7.7 | Advanced Admin Dashboard v2 | Enhanced /admin page | High |
| 7.8 | Gate 7 Governance Docs | 8+ L1-L3 documents | High |

Likelihood assessment based on Gate 6 output quality. If Gate 6 underperforms, Gate 7 scope may be reduced to focus on remediation.

# 4. Dependency Analysis on Gate 6 Outputs

Gate 7 cannot be planned in isolation. The following Gate 6 outputs are prerequisites for Gate 7 work packages.

| G7 Item | Depends On (G6) | Dependency Type | Risk if Missing |
| --- | --- | --- | --- |
| Analytics Dashboard | visitor_interaction table + all G6 routes | Data source | Cannot track what does not exist |
| Titan Performance Scoring | titan_conversation table | Data source | No conversation data to score |
| Knowledge Gap Detection | civilization.ask endpoint + 50+ articles | Query data + corpus size | Insufficient data for pattern detection |
| Civilization Health Score | All G6 tables + all metrics | Composite data | Incomplete health picture |
| Visitor Journey Tracking | All G6 + G5 routes | Navigation paths | Incomplete journey map |
| Corpus Batch 4 | P-01 pipeline (G6 WP 6.4) | Infrastructure | Must re-implement ingestion |

Critical path: All Gate 7 deliverables depend on Gate 6 routes and tables being operational. Gate 6 closure is a hard dependency for Gate 7 architecture freeze.

# 5. Candidate Work Packages [NOT FROZEN]

The following work packages are candidates only. They will be refined and frozen after Gate 6 closure and Founder review.

| WP | Candidate Work Package | Owner | Dependencies | Status |
| --- | --- | --- | --- | --- |
| 7.1 | Analytics Dashboard | Husam | G6: all routes, visitor_interaction | Candidate |
| 7.2 | Knowledge Gap Detection Engine | Husam | G6: ask endpoint, 50+ articles | Candidate |
| 7.3 | Titan Performance Scoring | Husam | G6: titan_conversation | Candidate |
| 7.4 | Visitor Journey Analytics | Husam | G6: all routes | Candidate |
| 7.5 | Civilization Health Score | Husam | G6: all tables + analytics | Candidate |
| 7.6 | Corpus Batch 4 Ingestion | Husam | G6: P-01 pipeline | Candidate |
| 7.7 | Admin Dashboard v2 | Husam | G6: admin route, analytics | Candidate |
| 7.8 | Governance Documentation | Kimi | G6: all deliverables | Candidate |

No work packages are frozen. Husam shall not begin implementation of any Gate 7 work package until ONX-G7AF-2026-001 (Architecture Freeze) is issued and accepted by the Founder.

# 6. Candidate Database Changes [NOT FROZEN]

The following tables are candidates for Gate 7. Schema is illustrative only and will be finalized after Gate 6 closure.

## 6.1 Candidate: analytics_event

CREATE TABLE analytics_event (id SERIAL PRIMARY KEY, event_type TEXT NOT NULL, route TEXT, titan_id TEXT, session_id TEXT, metadata JSONB, created_at TIMESTAMP DEFAULT NOW());

Purpose: Granular event tracking for all visitor interactions.

## 6.2 Candidate: titan_performance_score

CREATE TABLE titan_performance_score (id SERIAL PRIMARY KEY, titan_id TEXT NOT NULL, metric_type TEXT NOT NULL, score DECIMAL(4,3), period_start TIMESTAMP, period_end TIMESTAMP, created_at TIMESTAMP DEFAULT NOW());

Purpose: Time-series scoring per Titan per metric type.

## 6.3 Candidate: knowledge_gap

CREATE TABLE knowledge_gap (id SERIAL PRIMARY KEY, query_pattern TEXT NOT NULL, frequency INTEGER DEFAULT 1, suggested_topic TEXT, confidence DECIMAL(3,2), status TEXT DEFAULT 'open', created_at TIMESTAMP DEFAULT NOW());

Purpose: Tracks unanswerable query patterns for corpus prioritization.

## 6.4 Candidate: civilization_health_snapshot

CREATE TABLE civilization_health_snapshot (id SERIAL PRIMARY KEY, overall_score DECIMAL(4,3), knowledge_completeness DECIMAL(4,3), ai_performance DECIMAL(4,3), engagement_score DECIMAL(4,3), system_stability DECIMAL(4,3), snapshot_date TIMESTAMP DEFAULT NOW());

Purpose: Daily civilization health composite score.

Candidate table count: 4. Final count to be determined after Gate 6 review.

# 7. Candidate API Expansions [NOT FROZEN]

Candidate endpoints for Gate 7. Contracts are illustrative and will be finalized after architecture freeze.

## 7.1 analytics Router (New)

analytics.getOverview — input: { period: 'day'|'week'|'month' } | output: { totalVisitors, avgSessionDuration, topRoutes[], titanInteractions }

analytics.getTitanMetrics — input: { titanId: string, period: string } | output: { conversations, avgResponseQuality, topQueries[] }

analytics.getKnowledgeGaps — input: { limit?: number } | output: { gaps: Array<{pattern, frequency, suggestedTopic, confidence}> }

analytics.getHealthScore — input: {} | output: { overallScore, breakdown: { knowledge, ai, engagement, stability } }

## 7.2 civilization Router (Expanded)

civilization.reportGap — input: { query: string, expectedAnswer?: string } | output: { gapId: number, status: 'recorded' }

Candidate endpoint count: 5. Final count to be determined after architecture freeze.

# 8. Candidate AI Capability Expansions [NOT FROZEN]

AI services that may be developed in Gate 7, contingent on Gate 6 AI service performance.

•  gap-detector.ts — Analyzes civilization.ask query logs to identify patterns that returned low-confidence answers. Clusters similar queries. Suggests new corpus topics.

•  titan-scorer.ts — Evaluates Titan response quality using multiple signals: response length, source citation count, user engagement (follow-up vs. bounce), and semantic coherence.

•  health-calculator.ts — Composite score algorithm combining: knowledge coverage ratio, AI response quality average, visitor engagement rate, error rate, and system uptime.

•  journey-analyzer.ts — Processes visitor navigation paths to identify common journeys, drop-off points, and optimal content placement recommendations.

Candidate AI services: 4. All depend on Gate 6 AI services being operational and generating sufficient data for pattern detection.

# 9. Candidate Corpus Requirements

Corpus Batch 4 is tentatively planned for Gate 7. Topic and source documents require Founder input.

## 9.1 Corpus Batch 4 (Gate 7 Target)

•  Estimated size: 15-20 documents

•  Ingestion method: P-01 pipeline (from Gate 6) — no new ingestion infrastructure needed

•  Topic: [FOUNDER INPUT REQUIRED] — suggest based on knowledge gap analysis from Gate 7.2

•  Priority topics (hypothesis): Advanced veterinary surgery, exotic animal care, emerging zoonotic diseases, veterinary ethics case studies

## 9.2 Corpus Expansion Strategy

Gate 7 may shift from 'batch' ingestion to 'targeted' ingestion — using knowledge gap detection to identify exactly what topics are missing, then sourcing documents specifically for those gaps. This represents a strategic shift from volume-based to need-based corpus growth.

# 10. Governance Considerations [PROVISIONAL]

## 10.1 Analytics Data Privacy

•  Visitor analytics must not collect personally identifiable information (PII)

•  Session tracking uses anonymous IDs only — no IP storage, no fingerprinting

•  Analytics data retention: 90 days rolling (aligned with SECH audit requirements)

## 10.2 AI Transparency

•  Titan performance scores must be explainable — not black-box algorithms

•  Knowledge gap detection must show its reasoning — which queries, why flagged, confidence basis

•  Civilization health score methodology must be documented and auditable

## 10.3 Required Governance Documents (Candidate)

•  ONX-G7PP-2026-001 (this document) — already in production

•  ONX-G7MEP-2026-001 (Master Execution Package) — after Gate 6 closure

•  ONX-G7AF-2026-001 (Architecture Freeze) — after Gate 6 closure

•  ONX-G7CA-2026-001 (Closure Audit) — end of Gate 7

•  ONX-G7DVR-2026-001 (Deployment Verification Report) — end of Gate 7

•  ONX-ANALYTICS-GOV-2026-001 (Analytics Governance Framework) — new L1 document

•  ONX-DATA-PRIVACY-2026-001 (Data Privacy Charter) — new L1 document

•  ONX-CAR-UP-2026-003 (CAR Update Gate 7) — L2 document

# 11. Risk Assessment [PROVISIONAL]

| # | Risk | Severity | Probability | Impact on G7 | Mitigation |
| --- | --- | --- | --- | --- | --- |
| G7-R1 | Gate 6 delayed beyond Week 12 | High | Medium | G7 timeline compressed or deferred | Monitor G6 weekly; prepare G7 in parallel to minimize gap |
| G7-R2 | Gate 6 AI quality below threshold | High | Medium | G7 gap detection and scoring unreliable | G7 scope reduces to G6 remediation if AI quality < 70% |
| G7-R3 | Insufficient analytics data volume | Medium | Medium | Metrics not statistically meaningful | Require minimum 1000 interactions before analytics activation |
| G7-R4 | Founder unavailable for Batch 4 topic decision | Medium | Low | Batch 4 deferred to Gate 8 | Propose default topic (exotic animal care) as fallback |
| G7-R5 | Analytics infrastructure cost overrun | Low | Medium | Budget pressure on Gates 8-10 | Implement usage caps and data sampling for high-volume events |
| G7-R6 | Privacy compliance complexity | Medium | Low | Governance documentation delays | Begin privacy framework drafting in parallel with G6 |

# 12. Estimated Execution Timeline [PROVISIONAL]

Gate 7 estimated at 2 weeks (Week 12-13), contingent on Gate 6 completing by end of Week 11.

| Week | Candidate WPs | Candidate Deliverables | Trigger |
| --- | --- | --- | --- |
| Week 12 | 7.1, 7.2, 7.3, 7.6 | Analytics dashboard, gap detection, Titan scoring, Batch 4 ingestion | Gate 6 closure authorized |
| Week 13 | 7.4, 7.5, 7.7, 7.8 | Journey analytics, health score, admin v2, governance docs | Week 12 deliverables verified |

## 12.1 Milestones (Candidate)

•  M1 (Day 3): analytics_event table operational, first metrics flowing

•  M2 (Day 5): /analytics page live with real-time dashboard

•  M3 (Day 7): Knowledge gap detection running, first gaps identified

•  M4 (Day 10): Titan performance scores visible in admin dashboard

•  M5 (Day 12): Civilization health score calculated and displayed

•  M6 (Day 14): All governance docs complete, Gate 7 closure package ready

# 13. Gate 6 to Gate 7 Transition Plan

The following transition sequence ensures zero idle time between Gate 6 closure and Gate 7 commencement.

## 13.1 Pre-Transition (During Gate 6 Execution)

1. Kimi maintains this ONX-G7PP-2026-001 document, updating candidate items as Gate 6 evidence clarifies dependencies

2. Kimi drafts ONX-ANALYTICS-GOV-2026-001 (Analytics Governance) and ONX-DATA-PRIVACY-2026-001 (Privacy Charter) in parallel with Gate 6 governance work

3. Husam reports any Gate 6 architectural insights that affect Gate 7 planning

4. Founder reviews ONX-G7PP-2026-001 at Gate 6 midpoint to provide early direction

## 13.2 Transition Sequence (Gate 6 Closure → Gate 7 Start)

1. Gate 6 closure authorized by Founder (Day 0)

2. Kimi produces ONX-G7MEP-2026-001 (Master Execution Package) within 24 hours

3. Founder reviews and accepts ONX-G7MEP-2026-001 (Day 1)

4. Kimi produces ONX-G7AF-2026-001 (Architecture Freeze) within 24 hours

5. Founder accepts ONX-G7AF-2026-001 (Day 2)

6. Husam begins Gate 7 execution (Day 2 — zero idle time)

## 13.3 Transition Guardrails

•  Guardrail 1: No Gate 7 work begins before Gate 6 closure is authorized by Founder

•  Guardrail 2: No Gate 7 architecture freeze issued before Gate 6 closure

•  Guardrail 3: If Gate 6 exceeds Week 11 by more than 3 days, Gate 7 scope may be reduced to maintain 90-Day Program schedule

•  Guardrail 4: Founder may pause Gate 7 planning at any time to focus resources on Gate 6 completion

## 13.4 Decision Points

| Trigger | Decision |
| --- | --- |
| Gate 6 Day 7 (midpoint) | Founder reviews ONX-G7PP-2026-001, provides Batch 4 topic direction |
| Gate 6 closure | Founder authorizes ONX-G7MEP-2026-001 production |
| G7 MEP acceptance | Founder authorizes ONX-G7AF-2026-001 production |
| G7 AF acceptance | Husam begins execution |

ONX Civilization Systems

Gate 7 — Preparation Package

PROVISIONAL — All elements subject to change

© 2026 ONX Civilization Systems