EP-01 STAGING, OPERATIONAL & DEPLOYMENT READINESS EXECUTION PACKAGE

ONX-ATRP-2026-004  |  12 Workstreams  |  For: Husam

Classification: Supreme Founder Operational Execution Order  |  Priority: MAXIMUM

Current State: RUNTIME SMOKE VERIFIED / LOCAL OPERATIONAL BASELINE VERIFIED / EP-01 TECHNICAL BASELINE VERIFIED

Target State: STAGING READY / OPERATIONALLY READY / DEPLOYMENT READY

Production Deployment: PROHIBITED until separate Founder authorization

# EXECUTIVE SUMMARY

This package contains 12 workstreams advancing ONX from LOCAL VERIFIED to STAGING READY. Each workstream includes implementation specifications, deliverables, acceptance criteria, and evidence requirements.

ATRP-2026-003 identified 5 blockers preventing staging deployment. This package remediates all 5:

ISSUE-001: Authentication Missing → WS-01: Authentication Readiness

ISSUE-002: Frontend Build Not Validated → WS-06: CI/CD Readiness (includes frontend build)

ISSUE-004: No HTTPS/SSL → WS-09: Security Readiness + WS-10: Staging Deployment

ISSUE-005: No CI/CD Pipeline → WS-06: CI/CD Readiness

ISSUE-006: No Automated Backups → WS-08: Backup & Recovery Readiness

# WORKSTREAM SUMMARY

| WS | NAME | BLOCKER | PRIORITY | ESTIMATE |
| --- | --- | --- | --- | --- |
| WS-01 | Authentication Readiness | ISSUE-001 | CRITICAL | ~4h |
| WS-02 | Authorization Readiness | ISSUE-001 | CRITICAL | ~3h |
| WS-03 | Error Handling & Resilience | — | HIGH | ~3h |
| WS-04 | Health Checks | — | HIGH | ~2h |
| WS-05 | Observability & Monitoring | — | HIGH | ~4h |
| WS-06 | CI/CD Readiness | ISSUE-002,005 | CRITICAL | ~6h |
| WS-07 | Database Migration Readiness | — | MEDIUM | ~2h |
| WS-08 | Backup & Recovery Readiness | ISSUE-006 | HIGH | ~3h |
| WS-09 | Security Readiness | ISSUE-004 | HIGH | ~4h |
| WS-10 | Staging Deployment Readiness | — | CRITICAL | ~4h |
| WS-11 | Operational Readiness | — | MEDIUM | ~3h |
| WS-12 | Deployment Readiness Decision | — | CRITICAL | ~1h |

Total Estimated Effort: ~39 hours  |  Critical Path: WS-01 → WS-02 → WS-06 → WS-10

# WORKSTREAM 01: AUTHENTICATION READINESS

Implements complete authentication system: login, logout, session management, session expiration, protected routes, and authentication audit logging.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Auth Backend | Add auth router to tRPC with login/logout/register mutations. Use bcrypt for password hashing. JWT for session tokens (access + refresh). |
| Session Store | Store active sessions in SQLite (sessions table: id, userId, token, expiresAt, createdAt). Implement automatic cleanup of expired sessions. |
| JWT Configuration | Access token: 15min expiry. Refresh token: 7 days expiry. Secret from env variable AUTH_SECRET. |
| Login Flow | POST /trpc/auth.login → validate credentials → create session → return {accessToken, refreshToken, user} |
| Logout Flow | POST /trpc/auth.logout → invalidate session → clear tokens → return {success: true} |
| Session Validation | Every protected procedure validates Bearer token → checks session table → rejects if expired or invalid |
| Session Expiration | Automatic 15min access token expiry. Refresh token rotation on every use. Cleanup job runs every hour. |
| Protected Routes | Add requireAuth middleware to tRPC. Frontend route guards redirect unauthenticated users to /login. |
| User Identity | Include user object (id, name, email, role) in all auth responses. Available via useAuth hook. |
| Audit Logging | Log every auth event: login_attempt, login_success, login_failure, logout, session_expired, token_refresh. Store in app_logs table. |

Deliverables:

• Authentication Router (auth.ts) with login/logout/register/refresh

• Sessions table migration

• Auth middleware (requireAuth) for tRPC

• useAuth React hook

• Login page component

• Authentication Readiness Report

• Authentication Test Evidence (unit tests, integration tests)

Acceptance Criteria:

✓ Unauthorized users are blocked from all protected routes

✓ Valid login returns access token + refresh token + user object

✓ Logout invalidates session and clears tokens

✓ Expired access tokens reject with 401

✓ Valid refresh tokens issue new access token

✓ Session cleanup removes expired sessions

✓ All auth events logged to app_logs table

✓ Login page accessible at /login with form validation

Evidence Required:

📎 auth.ts router source code

📎 Sessions table schema migration

📎 requireAuth middleware implementation

📎 useAuth hook source code

📎 Login page component screenshot

📎 Test: login with valid credentials → 200 + tokens

📎 Test: login with invalid credentials → 401

📎 Test: access protected route without token → 401

📎 Test: access protected route with valid token → 200

📎 Test: logout → subsequent requests return 401

📎 Test: expired token → 401 + refresh token works

📎 Test: audit logs show auth events

Known Issues to Resolve:

⚠ Auth secret must be set in environment (AUTH_SECRET) — document in .env.example

⚠ bcrypt may have native dependencies — ensure it builds in target environment

⚠ JWT clock skew — allow 60s leeway for token validation

# WORKSTREAM 02: AUTHORIZATION READINESS

Implements role-based access control: role model, permission model, protected APIs, admin/user boundaries.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Role Model | 3 roles: founder (full access), admin (most access), operator (limited access). Stored in users.role enum. |
| Permission Model | Permission matrix: read, write, admin, execute. founder=ALL, admin=read+write+admin, operator=read+execute. |
| Protected APIs | Add requireRole middleware to tRPC. Checks ctx.user.role against required permission. Returns 403 if insufficient. |
| Protected tRPC Procedures | Mark procedures with .use(requireRole('admin')) or .use(requireRole('founder')). Public procedures remain accessible. |
| Admin Boundaries | Admin-only: userCreate, configSet, wpUpdateStatus, systemInfo mutations. User list and health check remain public. |
| Unauthorized Behavior | Return structured 403 with {code: FORBIDDEN, message, requiredRole, userRole}. Log unauthorized attempts. |

Deliverables:

• Authorization Matrix document (role × permission × route)

• requireRole middleware

• Protected tRPC procedure decorators

• Permission constants/types

• Authorization Test Evidence

Acceptance Criteria:

✓ Role enforcement verified for all admin routes

✓ Operator user cannot access admin endpoints → 403

✓ Founder user can access all endpoints → 200

✓ Unauthorized access attempts are logged

✓ Permission matrix matches Atlas authority model (AUTH-001 through AUTH-089)

Evidence Required:

📎 Authorization Matrix (spreadsheet/table)

📎 requireRole middleware source

📎 Test: operator accessing admin endpoint → 403

📎 Test: founder accessing admin endpoint → 200

📎 Test: unauthorized attempt logged in app_logs

📎 Permission matrix alignment with Atlas

# WORKSTREAM 03: ERROR HANDLING & RESILIENCE

Implements comprehensive error handling across all layers: global, API, tRPC, client boundaries, structured error responses.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Global Error Handler | Hono onError middleware catches all unhandled exceptions. Logs full stack trace. Returns JSON error response. |
| API Error Format | Standardized: {success: false, code: ERROR_CODE, message, details?, stack? (dev only), correlationId, timestamp} |
| tRPC Error Format | Custom error formatter: context adds correlationId, request path, user info. Client receives clean error shape. |
| Error Codes | System: INTERNAL_ERROR, NOT_FOUND, VALIDATION_ERROR, AUTHENTICATION_ERROR, AUTHORIZATION_ERROR, DATABASE_ERROR, EXTERNAL_SERVICE_ERROR |
| Client Error Boundaries | React ErrorBoundary at route level. Fallback UI shows error details + correlationId for support. |
| Runtime Exception Logging | All uncaught exceptions logged to app_logs with FATAL level. Process continues (do not crash on non-fatal). |
| Structured Error Responses | All API errors return application/json with proper HTTP status codes: 400 validation, 401 auth, 403 forbidden, 404 not found, 500 internal |
| Zod Error Handling | Validation errors return field-level details: {field: 'email', message: 'Invalid email format', code: 'invalid_string'} |

Deliverables:

• Error Handler Report

• Failure Simulation Evidence

• ErrorBoundary components

• Error code constants

Acceptance Criteria:

✓ No unhandled runtime exceptions crash the server

✓ All failures logged with correlationId

✓ User-facing failures show clean error UI

✓ API returns structured JSON errors with proper status codes

✓ Validation errors include field-level details

Evidence Required:

📎 errorHandler.ts source

📎 ErrorBoundary.tsx source

📎 errorCodes.ts constants

📎 Test: unhandled exception → caught + logged

📎 Test: validation error → 400 + field details

📎 Test: not found → 404 + code

📎 Test: ErrorBoundary renders fallback UI

# WORKSTREAM 04: HEALTH CHECKS

Implements comprehensive health check endpoints for endpoint, database, API, tRPC, and startup readiness.

## Implementation Specification

| ENDPOINT | SPECIFICATION |
| --- | --- |
| GET /health | Simple liveness check. Returns {status: 'ok', timestamp, version, uptime}. HTTP 200. |
| GET /health/ready | Readiness probe. Checks: database connection, memory usage < 90%, disk space > 10%. Returns detailed status per dependency. |
| GET /health/db | Database-specific check. Executes SELECT 1. Returns {connected: true, latency: '2ms', wal_mode: true}. |
| GET /health/api | API check. Verifies tRPC router loads. Returns {procedures: 18, status: 'ok'}. |
| GET /health/trpc | tRPC-specific check. Calls internal health procedure. Returns same as GET /health. |
| Startup Readiness | App waits for DB connection before accepting requests. Exponential backoff (max 30s). Fails fast if DB unreachable. |
| Health Response Format | {status: 'ok'¦'degraded'¦'down', checks: {database: {...}, memory: {...}, disk: {...}}, timestamp, version} |

Deliverables:

• Health Check Report

• Health Endpoint Evidence

• Startup readiness probe

Acceptance Criteria:

✓ Health endpoint returns valid status

✓ Dependency failure states are detectable (degraded/down)

✓ Database health includes connection latency

✓ Startup blocks until DB ready

✓ All 5 health endpoints respond correctly

Evidence Required:

📎 health.ts router source

📎 Startup probe implementation

📎 Test: GET /health → 200 + ok

📎 Test: GET /health/ready → all checks green

📎 Test: DB failure → degraded status

📎 Test: startup with DB down → retries then fails

# WORKSTREAM 05: OBSERVABILITY & MONITORING

Implements application logs, request logs, error logs, runtime metrics, monitoring hooks, dashboard readiness, and alert readiness.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Application Logs | Structured JSON logging via Pino. Levels: debug, info, warn, error, fatal. Includes: timestamp, level, message, context, correlationId, userId, path. |
| Request Logs | Hono logger middleware + custom: method, path, statusCode, duration, userAgent, ip. Stored in app_logs table. |
| Error Logs | All errors logged with full context. FATAL errors trigger immediate alert webhook. Stack traces in development only. |
| Runtime Metrics | Collect: request_count, request_duration, error_count, active_sessions, db_query_duration, memory_usage. Expose at /metrics (Prometheus format). |
| Monitoring Hooks | Pre-built hooks: onRequestStart, onRequestEnd, onError, onAuthEvent. Configurable to send to external systems. |
| Dashboard Readiness | Metrics table with time-series data. Frontend /system page shows real-time charts. Prometheus scrape endpoint ready. |
| Alert Readiness | Configurable thresholds: error_rate > 5%, response_time > 500ms, memory > 90%. Webhook alerts to PagerDuty/Slack when triggered. |

Deliverables:

• Observability Report

• Monitoring Readiness Report

• Prometheus /metrics endpoint

• Alert configuration

Acceptance Criteria:

✓ Logs captured in structured JSON format

✓ Request logs include duration and status code

✓ Error logs include full context + correlationId

✓ Runtime metrics exposed in Prometheus format

✓ Critical failures can trigger webhook alerts

✓ Dashboard shows real-time system metrics

Evidence Required:

📎 Pino logger configuration

📎 /metrics endpoint response sample

📎 Alert threshold config

📎 Test: request logged with duration

📎 Test: error logged with context

📎 Test: /metrics returns Prometheus format

📎 Dashboard screenshot with metrics

# WORKSTREAM 06: CI/CD READINESS

Implements GitHub Actions workflows for build, lint, test, environment validation, and deployment. Resolves ISSUE-002 (frontend build) and ISSUE-005 (CI/CD pipeline).

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| .github/workflows/ci.yml | Main CI pipeline. Triggers on push/PR to main. Jobs: lint (backend + frontend), build (backend + frontend), test (vitest), docker-build. |
| .github/workflows/deploy-staging.yml | Staging deployment. Trigger: CI success on main. Builds Docker images. Deploys to staging host. Runs smoke tests. |
| .github/workflows/lint.yml | Dedicated lint workflow. ESLint for backend. ESLint for frontend. Fails on any warning. |
| .github/workflows/test.yml | Test workflow. Runs vitest for backend. Code coverage report. Uploads to artifact. |
| Build Backend | tsc compilation. Output to dist/. Verify no type errors. |
| Build Frontend | vite build. Output to dist/. Verify no build errors. Bundle size check (< 500KB). |
| Docker Build | docker build for backend and frontend. Verify multi-stage builds. Image size < 200MB. |
| Environment Validation | Validate .env.example has all required vars. Check no secrets in code (gitleaks). |
| CI Failure Behavior | Any job failure blocks deployment. Slack/Discord notification on failure. Artifact retention: 30 days. |

Deliverables:

• CI/CD Configuration Package (4 workflow files)

• CI/CD Validation Report

• Build evidence

• Test report

Acceptance Criteria:

✓ Build pipeline passes for backend

✓ Build pipeline passes for frontend (resolves ISSUE-002)

✓ Lint pipeline passes with zero warnings

✓ Test pipeline executes all tests

✓ CI failure blocks deployment

✓ Docker images build successfully

Evidence Required:

📎 ci.yml source

📎 deploy-staging.yml source

📎 lint.yml source

📎 test.yml source

📎 Build log (backend): 0 errors

📎 Build log (frontend): 0 errors

📎 Lint report: 0 warnings

📎 Test report: all pass

📎 Docker build log

📎 gitleaks scan: no secrets found

Known Issues to Resolve:

⚠ Requires GitHub repository with Actions enabled

⚠ Docker registry credentials needed for image push

⚠ Staging host SSH key needed for deployment

# WORKSTREAM 07: DATABASE MIGRATION READINESS

Implements schema validation, migration process, rollback procedure, seed process, and local reset.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Schema Validation | drizzle-kit generate produces SQL. Manual review of generated SQL before applying. Schema diff tool for verification. |
| Migration Status | Migrations stored in db/migrations/. Migration journal tracked in _journal table. Each migration has sequential ID. |
| Repeatable Process | npm run db:migrate → drizzle-kit migrate → applies pending migrations → updates journal. Idempotent (safe to run multiple times). |
| Rollback Procedure | Each migration generates up.sql and down.sql. Rollback: execute down.sql in reverse order. Documented in MIGRATION_ROLLBACK.md. |
| Seed Process | npm run db:seed → executes seed.ts → inserts initial data. Safe to re-run (uses INSERT OR IGNORE / ON CONFLICT). |
| Local Reset | npm run db:reset → drops all tables → runs all migrations → runs seed. For development only. NEVER in production. |
| Staging Migration | Staging migration plan: backup first → apply migrations → verify → rollback plan ready. Documented in STAGING_MIGRATION_PLAN.md |

Deliverables:

• Database Migration Readiness Report

• Migration Evidence Package

• STAGING_MIGRATION_PLAN.md

• MIGRATION_ROLLBACK.md

Acceptance Criteria:

✓ Migrations are repeatable (idempotent)

✓ Rollback procedure documented and tested

✓ Database reset path verified for local dev

✓ Seed process inserts all required initial data

✓ Staging migration plan documented with backup step

Evidence Required:

📎 drizzle.config.ts

📎 Migration SQL files

📎 Test: db:migrate applies cleanly

📎 Test: db:migrate re-run → no-op

📎 Test: db:reset → clean state + seeded

📎 Rollback procedure documented

📎 Staging migration plan document

# WORKSTREAM 08: BACKUP & RECOVERY READINESS

Implements backup strategy, restore procedure, recovery process, data loss risk assessment, RTO/RPO targets. Resolves ISSUE-006.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Backup Strategy | SQLite file copy + WAL checkpoint. Automated via cron job every 6 hours. Retention: 7 daily + 4 weekly + 12 monthly. |
| Backup Storage | Primary: S3-compatible object storage (MinIO/AWS S3). Secondary: local volume mount. Encrypted at rest (AES-256). |
| Backup Script | scripts/backup.sh → sqlite3 onx.db '.backup /tmp/backup.db' → compress → encrypt → upload to S3 → verify checksum. |
| Restore Procedure | scripts/restore.sh → download from S3 → decrypt → decompress → verify checksum → stop app → replace db → start app → health check. |
| Recovery Process | Documented in RECOVERY_PROCEDURE.md. Step-by-step with estimated times. Point-in-time recovery using WAL + backups. |
| Data Loss Risk | SQLite WAL provides crash recovery (zero data loss on crash). Backup interval: 6h → max data loss: 6h of writes. |
| RTO Target | Recovery Time Objective: 15 minutes (download + restore + verify + restart). |
| RPO Target | Recovery Point Objective: 6 hours (backup frequency). |

Deliverables:

• Backup & Recovery Report

• Restore Procedure Evidence

• scripts/backup.sh

• scripts/restore.sh

• RECOVERY_PROCEDURE.md

Acceptance Criteria:

✓ Backup plan documented

✓ Restore procedure documented and testable

✓ Backup script executable and verified

✓ RTO ≤ 15 minutes

✓ RPO ≤ 6 hours

✓ Recovery path tested locally

Evidence Required:

📎 backup.sh source code

📎 restore.sh source code

📎 RECOVERY_PROCEDURE.md

📎 Test: backup script → S3 upload success

📎 Test: restore script → database recovered

📎 RTO/RPO calculation document

# WORKSTREAM 09: SECURITY READINESS

Implements secrets management, security headers, input validation, API protection, dependency review, and sensitive data exposure check. Resolves ISSUE-004 (HTTPS/SSL).

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Secrets Management | All secrets from environment variables. .env.example documents required vars. .env in .gitignore. Runtime validation on startup. |
| Environment Protection | NODE_ENV controls error detail (dev=stack traces, prod=generic messages). PORT, DATABASE_URL, AUTH_SECRET validated. |
| Security Headers | Hono + @hono/secure-headers: HSTS, X-Frame-Options, X-Content-Type-Options, CSP, Referrer-Policy. |
| Input Validation | Zod on ALL tRPC inputs. Additional: max length limits, sanitize strings (no HTML/JS). File upload validation (type, size). |
| API Protection | Rate limiting: 100 req/min per IP, 10 req/min per auth endpoint. CORS: restrict to known origins in production. |
| Dependency Review | npm audit on every build. Dependabot alerts enabled. Lock file committed. No known vulnerabilities in dependencies. |
| Sensitive Data Exposure | No PII in logs. Passwords hashed (bcrypt). Tokens encrypted in transit (HTTPS). Database encrypted at rest. |
| HTTPS/SSL | Production: nginx terminates SSL with Let's Encrypt. Staging: Cloudflare or self-signed cert. Development: HTTP acceptable. |

Deliverables:

• Security Readiness Assessment

• Security Findings Register

• Rate limiter config

• Security headers config

• CSP policy

Acceptance Criteria:

✓ No critical security findings

✓ All secrets in environment variables only

✓ Security headers on all responses

✓ Rate limiting active on all endpoints

✓ Input validation on all API inputs

✓ npm audit passes with zero vulnerabilities

✓ No sensitive data in logs or error responses

Evidence Required:

📎 Security headers response sample

📎 Rate limit test: 101st request → 429

📎 npm audit report

📎 gitleaks scan report

📎 CSP header value

📎 Test: SQL injection attempt → blocked

📎 Test: XSS attempt → sanitized

# WORKSTREAM 10: STAGING DEPLOYMENT READINESS

Prepares hosting target, database target, environment variables, build/start/deploy commands, health check route, rollback plan, and recovery plan.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Hosting Target | Staging: VPS or PaaS (Render/Railway/Fly.io). Minimum: 1 CPU, 1GB RAM, 10GB SSD. OS: Ubuntu 22.04 LTS. |
| Database Target | SQLite file on persistent volume. Path: /data/onx.db. WAL mode enabled. Volume mounted to container. |
| Environment Variables | .env.staging: NODE_ENV=staging, PORT=3000, DATABASE_URL=/data/onx.db, AUTH_SECRET=<generated>, API_URL=https://staging.onx.system |
| Build Command | docker-compose -f docker-compose.staging.yml build → builds backend + frontend images |
| Start Command | docker-compose -f docker-compose.staging.yml up -d → starts all services in background |
| Deploy Command | ./scripts/deploy-staging.sh → git pull → build → migrate → health check → notify |
| Health Check Route | GET /health → returns {status: 'ok', env: 'staging', version: '1.0.0'} → deployment verification |
| Rollback Plan | ./scripts/rollback-staging.sh → docker-compose down → docker pull previous-image → docker-compose up → health check. Keep last 3 image versions. |
| Recovery Plan | If deployment fails: automatic rollback to previous version. If data corruption: restore from backup (WS-08). Recovery time: < 15 min. |
| Staging Domain | staging.onx.system → A record to staging IP. SSL via Cloudflare or Let's Encrypt. Health check from external monitor (UptimeRobot). |

Deliverables:

• Staging Deployment Plan

• Staging Deployment Checklist

• docker-compose.staging.yml

• scripts/deploy-staging.sh

• scripts/rollback-staging.sh

• .env.staging.example

Acceptance Criteria:

✓ Staging deployment is reproducible from documented commands

✓ Environment requirements documented

✓ Rollback path documented and testable

✓ Health check verifies successful deployment

✓ SSL/HTTPS configured for staging domain

✓ Recovery plan documented with < 15 min RTO

Evidence Required:

📎 Staging deployment plan document

📎 docker-compose.staging.yml

📎 deploy-staging.sh source

📎 rollback-staging.sh source

📎 .env.staging.example

📎 Deployment checklist (all items checked)

# WORKSTREAM 11: OPERATIONAL READINESS

Prepares runbooks, incident response process, alert escalation path, support ownership, monitoring dashboard plan, operational checklist, and post-deployment verification checklist.

## Implementation Specification

| COMPONENT | SPECIFICATION |
| --- | --- |
| Runbooks | ONX_RUNBOOKS.md: Startup (docker-compose up), Shutdown (docker-compose down), Restart (docker-compose restart), Health Check (curl /health), Log Viewing (docker logs), Backup (scripts/backup.sh), Restore (scripts/restore.sh), Scale (docker-compose up --scale). |
| Incident Response | INCIDENT_RESPONSE.md: 1) Detect (alert/monitor), 2) Assess (severity/impact), 3) Contain (stop bleeding), 4) Resolve (fix root cause), 5) Verify (health checks), 6) Document (post-mortem). Classification: P1 (system down), P2 (degraded), P3 (minor). |
| Alert Escalation | Level 1: Automated webhook → Slack. Level 2: No acknowledgment in 15 min → SMS to on-call. Level 3: No acknowledgment in 30 min → Call to Founder. On-call rotation: Husam (primary), Kimi (secondary). |
| Support Ownership | Husam: System operations, deployment, monitoring. Kimi: Code changes, bug fixes, feature development. Founder: Strategic decisions, authorization, escalation. |
| Monitoring Dashboard | Grafana dashboard: Request rate, Error rate, Response time, Active users, DB size, Memory usage, CPU usage. Data source: Prometheus scraping /metrics. |
| Operational Checklist | Daily: Check /health, review error logs, check disk space. Weekly: Review metrics, check backup success, review security alerts. Monthly: Dependency updates, performance review, capacity planning. |
| Post-Deployment Verification | POST_DEPLOY_CHECKLIST.md: 1) /health returns ok, 2) All routes return 200, 3) Login works, 4) Key features functional, 5) No error spikes, 6) Metrics flowing, 7) Alerts configured, 8) Backup completed. |

Deliverables:

• Operational Readiness Report

• Runbook Package (ONX_RUNBOOKS.md)

• Incident Response Checklist (INCIDENT_RESPONSE.md)

• POST_DEPLOY_CHECKLIST.md

Acceptance Criteria:

✓ Operator can respond to failure using runbooks

✓ Critical incidents have escalation path (< 30 min to Founder)

✓ Post-deployment checks defined and executable

✓ Monitoring dashboard plan documented

✓ Support ownership clearly assigned

Evidence Required:

📎 ONX_RUNBOOKS.md

📎 INCIDENT_RESPONSE.md

📎 POST_DEPLOY_CHECKLIST.md

📎 Escalation path diagram

📎 Support ownership matrix

📎 Monitoring dashboard mockup

# WORKSTREAM 12: DEPLOYMENT READINESS DECISION

Final classification of ONX EP-01 readiness. After all 11 workstreams complete, classify as STAGING_READY, PARTIALLY_STAGING_READY, or REMEDIATION_REQUIRED.

## CLASSIFICATION CRITERIA

| CLASSIFICATION | CRITERIA |
| --- | --- |
| STAGING_READY | All 11 workstreams complete. All acceptance criteria met. Zero undocumented issues. All evidence collected. Staging deployment plan executable. |
| PARTIALLY_STAGING_READY | Most workstreams complete (8-10/11). Core functionality verified. Minor issues remain with documented workarounds. Staging deployment possible with known limitations. |
| REMEDIATION_REQUIRED | Fewer than 8 workstreams complete. Critical blockers remain. Cannot deploy to staging without additional work. |

## READINESS CHECKLIST

| WS | NAME | STATUS | VERIFICATION |
| --- | --- | --- | --- |
| WS-01 | Authentication Readiness | — | login/logout/session/protected routes |
| WS-02 | Authorization Readiness | — | roles/permissions/protected APIs |
| WS-03 | Error Handling & Resilience | — | global/API/tRPC/client boundaries |
| WS-04 | Health Checks | — | endpoint/DB/API/tRPC/startup |
| WS-05 | Observability & Monitoring | — | logs/metrics/dashboard/alerts |
| WS-06 | CI/CD Readiness | — | build/lint/test/deploy pipelines |
| WS-07 | Database Migration Readiness | — | schema/migrations/rollback/seed |
| WS-08 | Backup & Recovery Readiness | — | strategy/restore/RTO/RPO |
| WS-09 | Security Readiness | — | secrets/headers/input validation/dependencies |
| WS-10 | Staging Deployment Readiness | — | hosting/env/build/deploy/rollback |
| WS-11 | Operational Readiness | — | runbooks/incident response/escalation |

## REMAINING ISSUES REGISTER

All issues from ATRP-2026-003 plus any new issues discovered during remediation:

| ID | DESCRIPTION | SEVERITY | ASSIGNED WS | STATUS |
| --- | --- | --- | --- | --- |
| ISSUE-001 | Authentication Missing | CRITICAL | WS-01 | PENDING |
| ISSUE-002 | Frontend Build Not Validated | HIGH | WS-06 | PENDING |
| ISSUE-004 | No HTTPS/SSL | HIGH | WS-09 + WS-10 | PENDING |
| ISSUE-005 | No CI/CD Pipeline | HIGH | WS-06 | PENDING |
| ISSUE-006 | No Automated Backups | HIGH | WS-08 | PENDING |
| ISSUE-007 | No Rate Limiting | MEDIUM | WS-09 | PENDING |
| ISSUE-008 | No Error Alerting | MEDIUM | WS-05 | PENDING |
| ISSUE-009 | Single Database Instance | MEDIUM | WS-07 | PENDING |
| ISSUE-010 | TypeScript Strict Build | MEDIUM | WS-06 | PENDING |
| ISSUE-011 | No Input Sanitization Beyond Zod | LOW | WS-09 | PENDING |
| ISSUE-012 | Environment Variables Not Validated | LOW | WS-09 | PENDING |

## RECOMMENDED NEXT STEPS

1. Execute WS-01 (Authentication) — highest priority, unblocks all protected functionality

2. Execute WS-06 (CI/CD) in parallel with WS-01 — validates build pipeline

3. Execute WS-02 (Authorization) after WS-01 completes — depends on auth system

4. Execute WS-09 (Security) + WS-10 (Staging Deployment) — enable staging environment

5. Execute WS-03 through WS-05, WS-07, WS-08, WS-11 — fill operational gaps

6. Execute WS-12 (Decision) — classify readiness based on evidence

7. If STAGING_READY: Deploy to staging, execute post-deployment checks

8. If PARTIALLY_STAGING_READY: Deploy with documented limitations

9. If REMEDIATION_REQUIRED: Return to Kimi with specific gaps

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# FINAL EXECUTION PRINCIPLE

Atlas Governs.

Husam Executes.

Kimi Orchestrates.

Evidence Proves.

Staging Precedes Production.

Operational Readiness Precedes Production.

Production Requires Separate Founder Authorization.

Always.

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Document: ONX-ATRP-2026-004  |  12 Workstreams  |  For: Husam  |  Status: ISSUED

Classification: Supreme Founder Operational Execution Order  |  Priority: MAXIMUM

Atlas: FROZEN  |  Production: PROHIBITED without Founder authorization