ONX SYSTEMS

EP-02 Pre-Issuance Execution Package

Runtime & Service Layer

Document ID: ONX-EP02-PREP-2026-001

Version: 1.0 | Classification: PRE-ISSUANCE — READY BUT NOT ISSUED

Issuance Directive: ONX-EP02-PREP-2026-001

Issued: 2026-06-20

╔══════════════════════════════════════════════════════════════════╗
║  STATUS: PRE-ISSUANCE — READY FOR ISSUANCE BUT NOT ISSUED      ║
║  EP-01 READINESS GATE MUST BE REACHED BEFORE ISSUANCE          ║
╚══════════════════════════════════════════════════════════════════╝

# EXECUTIVE SUMMARY

This document constitutes the complete EP-02 Pre-Issuance Execution Package for the ONX Atlas V5.0 Realization Program. EP-02 (Runtime & Service Layer) is fully engineered, decomposed, traceable, and execution-ready. This package SHALL NOT be issued to Husam until EP-01 Readiness Gate is confirmed achieved.

Package Status

Package State: [PRE-ISSUANCE — ENGINEERED & READY]

Issuance Blocker: [EP-01 Readiness Gate (M-08)]

Engineering Status: [COMPLETE — All 10 deliverables produced]

Atlas Compliance: [FULL — All WPs traced to CAP/AUTH]

Optimization Analysis: [COMPLETE — 4 execution paths identified]

EP-02 Program Summary

Program ID: EP-02

Program Name: Runtime & Service Layer

Work Packages: 8

Estimated Duration: 10-14 weeks

Critical Path Length: 7 WPs sequential

Parallelizable WPs: 5 (WP-05, WP-06, WP-07 parallel after WP-03/04)

Maximum Throughput: 10 weeks (fast-track with full parallelization)

EP-01 Dependencies: 6 transition dependencies (Section 3)

EP-03 Deliverables: 8 transition outputs (Section 10)

Issuance Conditions

1. EP-01 M-08 milestone CONFIRMED (EP-01 COMPLETE)

2. Kimi verifies EP-02 Readiness Criteria (Section 9) satisfied

3. Founder acknowledges EP-01 completion

4. ONX-EP02-2026-001 Issuance Document generated

5. ONX-EHP-2026-002 (EP-02 Handover Package) derived from this pre-issuance package

6. Husam briefing session completed

# DELIVERABLE 1: EP-02 MASTER EXECUTION PACKAGE

This deliverable establishes the complete master package structure, authority framework, constitutional foundation, and integration architecture for EP-02. It serves as the container for all subsequent deliverables and defines the relationship between EP-02 and the broader ATRP-2026-001 execution framework.

1.1 Constitutional Foundation

Governing Directive: ATRP-2026-001 (Atlas V5.0 Realization Program)

Baseline Artifact: ONX Atlas V5.0 — FROZEN

Constitutional Level: Level 5 — Authorized Execution Program

Civilizational Objectives: CO-001 (Technical Excellence), CO-002 (Operational Integrity), CO-004 (Authority Continuity), CO-006 (System Evolution)

Preceding Program: EP-01 (Core Platform Infrastructure)

Following Program: EP-03 (User Experience & Interface)

1.2 Authority Model for EP-02

Constitutional Authority: Mohammed Shaheen (Founder) — CCR approval, scope changes, issuance decision

Atlas Custodian: Kimi — WP review, evidence validation, readiness gate confirmation

Execution Owner (Post-Issuance): Husam — WP execution, evidence submission, reporting

CCR Protocol: Active — All 4 CCR types (A/B/C/D) available per Atlas V5.0 CCR Protocol

1.3 EP-02 Integration Architecture

Input Interface: Receives EP-01 outputs (architecture, framework, database, API gateway, security, CI/CD)

Output Interface: Produces runtime services consumed by EP-03 (frontend), EP-04 (operations), EP-05 (intelligence)

Contract Stability: EP-02 shall not break EP-01 contracts without CCR-Type-C

Downstream Compatibility: All EP-02 service contracts must be versioned for EP-03+ consumption

1.4 Package Contents Inventory

| Deliverable | Description |
| --- | --- |
| Deliverable 1 | Master Execution Package (this section) |
| Deliverable 2 | Complete Work Package Breakdown — 8 WPs with full executable detail |
| Deliverable 3 | Dependency Mapping — WP→WP, WP→EP-01, cross-EP |
| Deliverable 4 | Atlas Traceability Mapping — CAP/AUTH references per WP |
| Deliverable 5 | Acceptance Criteria — per WP + program-level criteria |
| Deliverable 6 | Evidence Requirements — per WP + evidence registry structure |
| Deliverable 7 | Critical Path Analysis — sequential critical chain |
| Deliverable 8 | Parallelization Opportunities — 4 execution paths |
| Deliverable 9 | Runtime Realization Plan — from Atlas runtime definitions |
| Deliverable 10 | EP-02→EP-03 Transition Map — readiness gates and deliverables |
| Appendix A | Document History & Version Control |
| Appendix B | Reference Documents |
| Appendix C | Abbreviations & Terms |
| Appendix D | Issuance Activation Checklist |

════════════════════════════════════════════════════════════

# DELIVERABLE 2: COMPLETE WORK PACKAGE BREAKDOWN — 8 WORK PACKAGES

This deliverable contains the fully decomposed executable specification for all 8 EP-02 Work Packages. Each WP includes: Objective, Scope, Inputs, Outputs, Dependencies, Acceptance Criteria, Evidence Requirements, Atlas Constitutional References, Effort Estimate, and Parallelization Classification.

## WP-01: Runtime Environment Setup

PRIORITY: CRITICAL  |  EFFORT: 2-3 weeks

EXECUTION CLASS: SEQUENTIAL — Foundation for all other EP-02 WPs

WP-01.1 Objective

Establish the complete runtime execution environment for all EP-02 services. This includes process management, resource allocation, sandboxing, and the service host that loads and executes runtime code. WP-01 is the EP-02 foundation — all other WPs depend on it.

WP-01.2 Scope

Implement process lifecycle manager (start, stop, restart, monitor)

Build resource allocation engine (CPU, memory, I/O quotas)

Create sandboxed execution context for service isolation

Implement service host bootstrap and configuration loading

Build environment detection (development, staging, production)

Create runtime health monitoring and self-diagnostics

Implement graceful degradation under resource constraints

Build runtime telemetry collection (performance counters)

WP-01.3 Inputs

EP-01 WP-01: System Architecture & ADRs

EP-01 WP-02: Base Service Framework (DI container, service registration)

Atlas V5.0 CAP-001 (Core Runtime Framework)

Atlas V5.0 CAP-002 (Service Management)

Atlas V5.0 CAP-014 (Environment Management)

WP-01.4 Outputs

Runtime Environment Manager implementation

Resource Allocation Engine with quota enforcement

Sandboxed Execution Context

Service Host Bootstrap module

Environment detection and configuration system

Runtime health monitoring dashboard

Resource constraint degradation policies

Runtime telemetry stream

WP-01 Evidence Package

WP-01.5 Dependencies

EP-01 WP-01 COMPLETE — Architecture decisions binding

EP-01 WP-02 COMPLETE — Service framework operational

EP-01 WP-05 COMPLETE — Configuration system active

WP-01.6 Acceptance Criteria

AC-01: Process lifecycle manager correctly starts, monitors, stops, and restarts services

AC-02: Resource quotas enforced — service exceeding CPU/memory limits is throttled/terminated

AC-03: Sandboxed context prevents service A from accessing service B memory/resources

AC-04: Service host bootstraps and loads configuration within 5 seconds

AC-05: Environment correctly detected and appropriate config loaded (dev/staging/prod)

AC-06: Health monitoring reports accurate status for all managed processes

AC-07: Graceful degradation activates when resources exceed 85% utilization

AC-08: Telemetry stream captures CPU, memory, request rate metrics every 10 seconds

AC-09: Unit test coverage ≥80%, integration tests cover all lifecycle operations

WP-01.7 Evidence Requirements

EV-01: Process lifecycle test results (start/stop/restart/monitor)

EV-02: Resource quota enforcement test (CPU/memory limit simulation)

EV-03: Sandbox isolation penetration test (negative test)

EV-04: Bootstrap timing benchmark (5-second target)

EV-05: Environment detection test across all three environments

EV-06: Health monitoring dashboard screenshot

EV-07: Degradation policy activation under load test

EV-08: Telemetry stream sample with all required metrics

EV-09: Code coverage report (≥80%)

WP-01.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-001, CAP-002, CAP-014, CAP-015, AUTH-002, AUTH-006, AUTH-024

════════════════════════════════════════════════════════════

## WP-02: Data Service Layer

PRIORITY: CRITICAL  |  EFFORT: 2-3 weeks

EXECUTION CLASS: SEQUENTIAL — Depends on WP-01

WP-02.1 Objective

Implement the complete data service layer providing CRUD operations, data validation, query optimization, caching, and transaction management. This is the primary data access layer consumed by EP-03 frontend and EP-05 intelligence services.

WP-02.2 Scope

Implement generic CRUD service base with repository pattern

Build data validation framework (input sanitization, schema validation)

Create query builder with optimization hints

Implement caching layer (L1 in-memory, L2 distributed)

Build transaction coordinator (distributed transactions)

Create data access audit logging

Implement batch operation support (bulk insert, update, delete)

Build data migration and seeding service

Create query performance analyzer and slow-query detection

WP-02.3 Inputs

EP-01 WP-03: Database & Persistence Layer (schema, migrations, repositories)

EP-02 WP-01: Runtime Environment (service host, resource management)

Atlas V5.0 CAP-005 (Data Persistence)

Atlas V5.0 CAP-006 (Data Integrity)

WP-02.4 Outputs

Generic CRUD Service implementation

Data Validation Framework

Query Builder with optimization

Multi-tier Caching Service (L1/L2)

Transaction Coordinator

Data Access Audit Logger

Batch Operations Service

Query Performance Analyzer

WP-02 Evidence Package

WP-02.5 Dependencies

EP-01 WP-03 COMPLETE — Database layer operational

EP-02 WP-01 COMPLETE — Runtime environment hosting services

WP-02.6 Acceptance Criteria

AC-01: CRUD operations work for all entity types with correct repository pattern

AC-02: Validation framework rejects invalid data with descriptive error messages

AC-03: Query builder generates optimized SQL with execution plan analysis

AC-04: Cache hit rate ≥85% for repeated queries under test load

AC-05: Distributed transactions commit/rollback atomically across multiple operations

AC-06: Every data access operation logged with user, timestamp, operation, result

AC-07: Batch operations process 10,000 records in <30 seconds

AC-08: Slow query detection flags queries exceeding 500ms threshold

AC-09: Integration tests cover all CRUD operations with ≥80% coverage

WP-02.7 Evidence Requirements

EV-01: CRUD test matrix (create/read/update/delete for all entities)

EV-02: Validation test results (valid/invalid/boundary cases)

EV-03: Query execution plan comparison (optimized vs unoptimized)

EV-04: Cache performance test (hit rate under load)

EV-05: Distributed transaction rollback test (simulated failure)

EV-06: Audit log sample showing complete data access trail

EV-07: Batch operation timing benchmark (10K records)

EV-08: Slow query detection alert sample

EV-09: Integration test coverage report

WP-02.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-005, CAP-006, CAP-007, CAP-024, AUTH-003, AUTH-007, AUTH-015

════════════════════════════════════════════════════════════

## WP-03: Service Endpoint Implementation

PRIORITY: HIGH  |  EFFORT: 2-3 weeks

EXECUTION CLASS: PARALLELIZABLE with WP-02 (after WP-01)

WP-03.1 Objective

Implement all service endpoints including RESTful API resources, GraphQL schema and resolvers, and WebSocket real-time handlers. These endpoints expose EP-02 services to EP-03 frontend and external consumers.

WP-03.2 Scope

Implement RESTful resource controllers for all domain entities

Build GraphQL schema with types, queries, mutations, subscriptions

Create GraphQL resolver layer connecting to data services

Implement WebSocket handlers for real-time features

Build request/response DTOs with AutoMapper-style mapping

Create API versioning middleware (v1, v2 support)

Implement request throttling and rate limiting per endpoint

Build API documentation generator (OpenAPI/Swagger + GraphQL Playground)

Create endpoint authorization policies (RBAC integration)

WP-03.3 Inputs

EP-01 WP-04: API Gateway (routing, middleware pipeline)

EP-02 WP-01: Runtime Environment (service hosting)

EP-02 WP-02: Data Service Layer (CRUD operations, validation)

Atlas V5.0 CAP-003 (Integration Interface)

Atlas V5.0 CAP-009 (API Management)

Atlas V5.0 CAP-011 (Communication Protocol)

WP-03.4 Outputs

RESTful Controller implementations (all domain entities)

GraphQL Schema (types, queries, mutations, subscriptions)

GraphQL Resolver layer

WebSocket Handler implementations

DTO mapping layer

API Versioning middleware

Endpoint-level rate limiting configuration

Auto-generated API documentation

Endpoint RBAC policy definitions

WP-03 Evidence Package

WP-03.5 Dependencies

EP-01 WP-04 COMPLETE — API gateway routing

EP-02 WP-01 COMPLETE — Runtime hosting

EP-02 WP-02 COMPLETE or PARALLEL — Data services (CRUD for endpoints)

WP-03.6 Acceptance Criteria

AC-01: All RESTful endpoints return correct HTTP status codes (200, 201, 204, 400, 401, 403, 404, 500)

AC-02: GraphQL queries resolve correctly with ≤200ms response time for simple queries

AC-03: GraphQL mutations correctly create/update/delete resources

AC-04: WebSocket connections maintain real-time updates with <100ms latency

AC-05: DTO mapping correctly transforms between domain and API models

AC-06: API versioning routes requests to correct version handlers

AC-07: Rate limiting blocks requests exceeding configured thresholds

AC-08: OpenAPI spec generated and validated against all endpoints

AC-09: RBAC policies correctly allow/deny access per endpoint and user role

AC-10: Contract tests pass for all API endpoints

WP-03.7 Evidence Requirements

EV-01: REST endpoint test results (all status codes covered)

EV-02: GraphQL query timing benchmark (≤200ms)

EV-03: GraphQL mutation test results (CRUD operations)

EV-04: WebSocket latency test (<100ms target)

EV-05: DTO mapping validation test

EV-06: API versioning routing test

EV-07: Rate limiting enforcement test

EV-08: OpenAPI specification document

EV-09: RBAC policy test matrix

EV-10: Contract test execution results

WP-03.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-003, CAP-009, CAP-011, CAP-025, AUTH-004, AUTH-012, AUTH-025

════════════════════════════════════════════════════════════

## WP-04: Security Service Layer

PRIORITY: HIGH  |  EFFORT: 2 weeks

EXECUTION CLASS: PARALLELIZABLE with WP-02 (after WP-01)

WP-04.1 Objective

Build the operational security services that protect all EP-02 endpoints and data. Includes token management, permission evaluation, audit logging, key rotation, and threat detection. This extends EP-01 security core with service-layer policies.

WP-04.2 Scope

Implement JWT token issuance, validation, and refresh service

Build permission evaluation engine (policy-based access control)

Create API key management service (generation, revocation, rotation)

Implement security audit logging (all authz decisions logged)

Build encryption key lifecycle management (creation, rotation, retirement)

Create anomaly detection for authentication patterns

Implement session management (creation, expiry, revocation)

Build security policy configuration and hot-reload

Create security incident response hooks (alerting integration)

WP-04.3 Inputs

EP-01 WP-06: Security & Authentication Core (auth framework, RBAC base)

EP-02 WP-01: Runtime Environment (service hosting)

EP-02 WP-03: Service Endpoints (endpoint definitions for protection)

Atlas V5.0 CAP-004 (Security Framework)

Atlas V5.0 CAP-012 (Identity Management)

Atlas V5.0 CAP-013 (Access Control)

WP-04.4 Outputs

Token Management Service (issue/validate/refresh)

Permission Evaluation Engine

API Key Management Service

Security Audit Logger

Encryption Key Lifecycle Manager

Authentication Anomaly Detector

Session Management Service

Security Policy Configuration System

Security Incident Response Hooks

WP-04 Evidence Package

WP-04.5 Dependencies

EP-01 WP-06 COMPLETE — Security core framework

EP-02 WP-01 COMPLETE — Runtime hosting

EP-02 WP-03 COMPLETE or PARALLEL — Endpoints to protect

WP-04.6 Acceptance Criteria

AC-01: JWT tokens issued with correct claims, expiry, and signature

AC-02: Token validation rejects expired, tampered, and revoked tokens

AC-03: Permission engine evaluates policies correctly (allow/deny/indeterminate)

AC-04: API keys generated with configurable scopes and expiry

AC-05: All authorization decisions logged with context (who, what, when, result)

AC-06: Key rotation completes without service interruption (zero-downtime)

AC-07: Anomaly detection flags unusual authentication patterns within 5 minutes

AC-08: Sessions correctly expire and can be remotely revoked

AC-09: Security policies reload without service restart

AC-10: Incident response hooks trigger within 30 seconds of security event

WP-04.7 Evidence Requirements

EV-01: JWT token lifecycle test (issue/validate/expire/refresh)

EV-02: Token tampering rejection test

EV-03: Permission evaluation matrix (all policy combinations)

EV-04: API key generation and scope validation

EV-05: Security audit log sample (complete decision trail)

EV-06: Key rotation zero-downtime verification

EV-07: Anomaly detection alert sample

EV-08: Session expiry and revocation test

EV-09: Policy hot-reload demonstration

EV-10: Incident hook trigger timing test

WP-04.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-004, CAP-012, CAP-013, CAP-026, AUTH-011, AUTH-013, AUTH-014, AUTH-026

════════════════════════════════════════════════════════════

## WP-05: External Integration Services

PRIORITY: MEDIUM  |  EFFORT: 2 weeks

EXECUTION CLASS: PARALLELIZABLE after WP-03/WP-04 (Phase 3)

WP-05.1 Objective

Implement the external integration layer for third-party APIs, webhook processing, file import/export, and legacy system adapters. This WP enables the ONX platform to connect with external services and data sources.

WP-05.2 Scope

Implement generic HTTP client with resilience patterns (retry, circuit breaker, timeout)

Build webhook receiver and processor (signature verification, queueing)

Create file import/export service (CSV, JSON, XML, Excel)

Build adapter framework for legacy system integration

Implement integration health monitoring (external service availability)

Create integration configuration management (endpoint URLs, credentials)

Build integration testing harness (mock external services)

Implement integration audit logging (all external calls logged)

WP-05.3 Inputs

EP-01 WP-08: Integration Framework (plugin system, adapter base)

EP-02 WP-01: Runtime Environment (service hosting)

EP-02 WP-04: Security Service (API key management, auth for external calls)

Atlas V5.0 CAP-003 (Integration Interface)

Atlas V5.0 CAP-016 (External Connectivity)

WP-05.4 Outputs

Resilient HTTP Client with circuit breaker

Webhook Receiver and Processor

File Import/Export Service

Legacy System Adapter Framework

Integration Health Monitor

Integration Configuration Manager

Integration Testing Harness

Integration Audit Logger

WP-05 Evidence Package

WP-05.5 Dependencies

EP-01 WP-08 COMPLETE — Integration framework base

EP-02 WP-01 COMPLETE — Runtime hosting

EP-02 WP-04 COMPLETE — Security services for external auth

WP-05.6 Acceptance Criteria

AC-01: HTTP client retries transient failures (3 attempts with exponential backoff)

AC-02: Circuit breaker opens after 5 consecutive failures, closes after recovery period

AC-03: Webhook signature verification rejects invalid payloads

AC-04: File import correctly parses all supported formats (CSV, JSON, XML, Excel)

AC-05: Adapter framework successfully connects to at least 2 sample legacy systems

AC-06: Health monitor correctly reports external service up/down status

AC-07: All external API calls logged with request/response summary

AC-08: Integration tests run with mocked external services (no live dependencies)

WP-05.7 Evidence Requirements

EV-01: Retry test with simulated failures

EV-02: Circuit breaker state transition demonstration

EV-03: Webhook signature verification (valid/invalid)

EV-04: File import test across all 4 formats

EV-05: Sample legacy adapter implementation (2 systems)

EV-06: Health monitor dashboard screenshot

EV-07: Integration audit log sample

EV-08: Mock integration test execution results

WP-05.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-003, CAP-016, CAP-017, CAP-027, AUTH-018, AUTH-019, AUTH-027

════════════════════════════════════════════════════════════

## WP-06: Background Job System

PRIORITY: MEDIUM  |  EFFORT: 1-2 weeks

EXECUTION CLASS: PARALLELIZABLE after WP-03/WP-04 (Phase 3)

WP-06.1 Objective

Implement the background job processing system including queue management, job scheduling, retry logic, dead-letter handling, and job monitoring. This enables asynchronous processing for long-running tasks.

WP-06.2 Scope

Implement job queue manager (multiple queue support)

Build job scheduler (cron-style and one-time scheduling)

Create job worker pool with concurrency control

Implement retry logic with exponential backoff and max retry policy

Build dead-letter queue for failed jobs exceeding retry limit

Create job monitoring dashboard (pending, running, completed, failed)

Implement job prioritization (critical, high, normal, low)

Build job idempotency keys to prevent duplicate execution

WP-06.3 Inputs

EP-02 WP-01: Runtime Environment (process management, resource quotas)

EP-02 WP-02: Data Service Layer (job state persistence)

Atlas V5.0 CAP-028 (Background Processing)

WP-06.4 Outputs

Job Queue Manager

Job Scheduler Service

Worker Pool with concurrency control

Retry Engine with backoff

Dead Letter Queue Handler

Job Monitoring Dashboard

Job Priority System

Idempotency Key Manager

WP-06 Evidence Package

WP-06.5 Dependencies

EP-02 WP-01 COMPLETE — Runtime environment for workers

EP-02 WP-02 COMPLETE — Data persistence for job state

WP-06.6 Acceptance Criteria

AC-01: Jobs enqueued and processed in FIFO order within priority class

AC-02: Scheduler triggers jobs at correct times (cron accuracy within 1 minute)

AC-03: Worker pool respects concurrency limits (no overflow)

AC-04: Failed jobs retried with exponential backoff (delays: 1min, 2min, 4min, 8min...)

AC-05: Jobs exceeding max retries (5) moved to dead-letter queue with full context

AC-06: Monitoring dashboard shows accurate real-time job status

AC-07: Higher priority jobs processed before lower priority jobs

AC-08: Duplicate job submission with same idempotency key processed exactly once

WP-06.7 Evidence Requirements

EV-01: Job enqueue and processing order test

EV-02: Scheduler accuracy test (cron trigger verification)

EV-03: Concurrency limit enforcement test

EV-04: Retry backoff timing verification

EV-05: Dead letter queue sample with failed job context

EV-06: Monitoring dashboard screenshot

EV-07: Priority ordering test (mixed priorities enqueued)

EV-08: Idempotency test (duplicate submission rejected)

WP-06.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-028, CAP-015, AUTH-028, AUTH-029

════════════════════════════════════════════════════════════

## WP-07: Notification Service

PRIORITY: MEDIUM  |  EFFORT: 1-2 weeks

EXECUTION CLASS: PARALLELIZABLE after WP-03/WP-04 (Phase 3)

WP-07.1 Objective

Build the multi-channel notification service supporting email, SMS, push notifications, and in-app notifications. Includes template management, delivery tracking, preference management, and rate limiting.

WP-07.2 Scope

Implement notification dispatcher (multi-channel routing)

Build email service (SMTP integration, template engine, attachment support)

Create SMS gateway integration (provider abstraction)

Implement push notification service (FCM/APNS abstraction)

Build in-app notification system (real-time delivery via WebSocket)

Create notification template management (CRUD, versioning)

Implement user preference management (channel preferences, opt-out)

Build delivery tracking and confirmation system

Create notification rate limiting (prevent spam)

WP-07.3 Inputs

EP-02 WP-01: Runtime Environment (service hosting)

EP-02 WP-03: Service Endpoints (notification API)

EP-02 WP-06: Background Jobs (async notification delivery)

Atlas V5.0 CAP-029 (Notification Management)

WP-07.4 Outputs

Notification Dispatcher

Email Service with templates

SMS Gateway Adapter

Push Notification Service

In-App Notification System

Template Management API

User Preference Service

Delivery Tracking System

Notification Rate Limiter

WP-07 Evidence Package

WP-07.5 Dependencies

EP-02 WP-01 COMPLETE — Runtime hosting

EP-02 WP-03 COMPLETE — API endpoints for notification CRUD

EP-02 WP-06 COMPLETE — Async job processing for delivery

WP-07.6 Acceptance Criteria

AC-01: Notifications routed to correct channel based on type and user preferences

AC-02: Email delivered with correct template, variables, and attachments

AC-03: SMS delivered through gateway with delivery receipt tracking

AC-04: Push notifications received on target devices within 5 seconds

AC-05: In-app notifications appear in real-time via WebSocket

AC-06: Templates versioned and can be updated without code deployment

AC-07: User preferences respected (opt-out channels not used)

AC-08: Delivery status tracked (sent/delivered/failed) for all channels

AC-09: Rate limiting prevents >100 notifications per user per hour

WP-07.7 Evidence Requirements

EV-01: Multi-channel routing test (email vs SMS vs push)

EV-02: Email template rendering test with variables

EV-03: SMS delivery receipt sample

EV-04: Push notification timing test (≤5 seconds)

EV-05: In-app real-time delivery demonstration

EV-06: Template versioning update demonstration

EV-07: Preference opt-out compliance test

EV-08: Delivery tracking report sample

EV-09: Rate limiting enforcement test

WP-07.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-029, CAP-011, CAP-028, AUTH-030, AUTH-031

════════════════════════════════════════════════════════════

## WP-08: Continuous Deployment & Environment Management

PRIORITY: HIGH  |  EFFORT: 1-2 weeks

EXECUTION CLASS: SEQUENTIAL — Final WP, depends on all prior

WP-08.1 Objective

Extend EP-01 CI/CD pipeline for EP-02 specific deployment needs including blue-green deployment, feature flags for service rollout, environment promotion automation, and deployment verification for EP-02 services.

WP-08.2 Scope

Extend CI/CD pipeline for EP-02 service builds and tests

Implement blue-green deployment for zero-downtime releases

Build feature flag integration for gradual service rollout

Create environment promotion pipeline (dev→staging→production)

Implement automated deployment verification (smoke tests post-deploy)

Build rollback automation for EP-02 services

Create deployment audit trail (who, what, when, where)

Implement canary deployment support (percentage-based traffic shifting)

WP-08.3 Inputs

EP-01 WP-10: CI/CD Pipeline & Deployment Foundation (base pipeline)

EP-02 WP-01: Runtime Environment (deployment target)

All EP-02 WPs 01-07: Services to deploy

Atlas V5.0 CAP-021 (Deployment Automation)

Atlas V5.0 CAP-022 (Release Management)

WP-08.4 Outputs

Extended CI/CD pipeline (EP-01 + EP-02 services)

Blue-Green Deployment implementation

Feature Flag Rollout integration

Environment Promotion Pipeline

Automated Deployment Verification

Rollback Automation for EP-02

Deployment Audit Trail

Canary Deployment Support

WP-08 Evidence Package

WP-08.5 Dependencies

EP-01 WP-10 COMPLETE — Base CI/CD pipeline operational

EP-02 WP-01 through WP-07 ALL COMPLETE — Services to deploy

WP-08.6 Acceptance Criteria

AC-01: EP-02 services build, test, and deploy through extended pipeline

AC-02: Blue-green deployment switches traffic with zero downtime (<1 second interruption)

AC-03: Feature flags control service rollout (enable/disable without deployment)

AC-04: Environment promotion automated with approval gates between stages

AC-05: Smoke tests verify deployment before marking successful

AC-06: Rollback completes in <3 minutes to previous stable version

AC-07: Every deployment logged with full audit trail (who, what, when, target)

AC-08: Canary deployment shifts traffic gradually (10%→50%→100%) with automatic rollback on error rate threshold

AC-09: Full pipeline execution (build through deploy) completes in <20 minutes

WP-08.7 Evidence Requirements

EV-01: Extended pipeline execution log (successful)

EV-02: Blue-green switch timing measurement (zero-downtime verification)

EV-03: Feature flag toggle demonstration (service on/off)

EV-04: Environment promotion automation log

EV-05: Smoke test results from deployment verification

EV-06: Rollback execution timing (<3 minutes)

EV-07: Deployment audit trail sample

EV-08: Canary traffic shift visualization (10→50→100%)

EV-09: End-to-end pipeline timing report (<20 min)

WP-08.8 Atlas Constitutional References

Referenced Capabilities & Authorities: CAP-021, CAP-022, CAP-014, CAP-030, AUTH-022, AUTH-023, AUTH-032

════════════════════════════════════════════════════════════

# DELIVERABLE 3: DEPENDENCY MAPPING

This deliverable maps all dependencies across three dimensions: (1) internal WP→WP dependencies within EP-02, (2) EP-01→EP-02 transition dependencies, and (3) cross-EP dependencies (EP-02→EP-03+). Dependencies are ABSOLUTE — no WP may begin before all upstream dependencies are COMPLETE.

3.1 Internal WP→WP Dependency Matrix (EP-02)

| WP | WP-01 | WP-02 | WP-03 | WP-04 | WP-05 | WP-06 | WP-07 | WP-08 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP-01 | — |  |  |  |  |  |  |  |
| WP-02 | D | — |  |  |  |  |  |  |
| WP-03 | D | D | — |  |  |  |  |  |
| WP-04 | D |  | D | — |  |  |  |  |
| WP-05 | D |  |  | D | — |  |  |  |
| WP-06 | D | D |  |  |  | — |  |  |
| WP-07 | D |  | D |  |  | D | — |  |
| WP-08 | D | D | D | D | D | D | D | — |

LEGEND: D = Direct dependency  |  — = Self  |  Green = No dependency (can parallelize)

3.2 EP-01 → EP-02 Transition Dependencies

| Transition | Purpose | Priority |
| --- | --- | --- |
| EP-01 WP-01 → EP-02 WP-01 | Architecture decisions bind EP-02 runtime design | CRITICAL |
| EP-01 WP-02 → EP-02 WP-01 | Service framework hosts EP-02 runtime services | CRITICAL |
| EP-01 WP-03 → EP-02 WP-02 | Database schema is data service foundation | CRITICAL |
| EP-01 WP-04 → EP-02 WP-03 | API gateway routes EP-02 endpoints | CRITICAL |
| EP-01 WP-05 → EP-02 WP-01 | Configuration system supports runtime env detection | HIGH |
| EP-01 WP-06 → EP-02 WP-04 | Security core is foundation for security services | CRITICAL |
| EP-01 WP-08 → EP-02 WP-05 | Integration framework hosts external adapters | HIGH |
| EP-01 WP-10 → EP-02 WP-08 | CI/CD pipeline deploys EP-02 services | CRITICAL |

3.3 EP-02 → EP-03+ Cross-Program Dependencies

| Cross-EP Dependency | Purpose | Priority |
| --- | --- | --- |
| EP-02 WP-03 → EP-03 WP-01 | REST/GraphQL endpoints consumed by frontend app shell | CRITICAL |
| EP-02 WP-03 → EP-03 WP-02 | API contracts for UI component data binding | HIGH |
| EP-02 WP-04 → EP-03 WP-03 | Security services protect dashboard access | HIGH |
| EP-02 WP-02 → EP-05 WP-01 | Data services feed analytics engine | MEDIUM |
| EP-02 WP-06 → EP-05 WP-02 | Job system executes automation workflows | MEDIUM |
| EP-02 WP-07 → EP-03 WP-04 | Notification service supports management alerts | MEDIUM |
| EP-02 WP-08 → EP-04 WP-01 | Deployment pipeline provisions infrastructure | HIGH |
| EP-02 WP-01 → EP-04 WP-02 | Runtime metrics feed monitoring system | MEDIUM |

════════════════════════════════════════════════════════════

# DELIVERABLE 4: ATLAS TRACEABILITY MAPPING

This deliverable maps every EP-02 Work Package to its governing Atlas V5.0 Capabilities and Authorities. Each WP is traceable through a constitutional chain: Civilizational Objective → Capability → Authority → Work Package. This mapping enables constitutional compliance verification and CCR impact assessment.

4.1 Civilizational Objective → EP-02 Mapping

| CO ID | Objective | Primary WPs | Coverage |
| --- | --- | --- | --- |
| CO-001 | Technical Excellence | WP-01, WP-02, WP-03, WP-08 | All EP-02 WPs |
| CO-002 | Operational Integrity | WP-01, WP-04, WP-06, WP-08 | Runtime, security, jobs, deployment |
| CO-003 | Constitutional Fidelity | ALL WPs | Every WP references Atlas CAP/AUTH |
| CO-004 | Authority Continuity | WP-04, WP-08 | Security services, deployment pipeline |
| CO-005 | Evidence Integrity | ALL WPs | Every WP has evidence requirements |
| CO-006 | System Evolution | WP-05, WP-08 | Integration services, deployment automation |

4.2 Capability → WP Mapping

| Capability | Name | Mapped WPs |
| --- | --- | --- |
| CAP-001 | Core Runtime Framework | WP-01 |
| CAP-002 | Service Management | WP-01 |
| CAP-003 | Integration Interface | WP-03, WP-05 |
| CAP-004 | Security Framework | WP-04 |
| CAP-005 | Data Persistence | WP-02 |
| CAP-006 | Data Integrity | WP-02 |
| CAP-007 | Observability | WP-01 (telemetry) |
| CAP-009 | API Management | WP-03 |
| CAP-011 | Communication Protocol | WP-03, WP-07 |
| CAP-012 | Identity Management | WP-04 |
| CAP-013 | Access Control | WP-04 |
| CAP-014 | Environment Management | WP-01, WP-08 |
| CAP-015 | Monitoring | WP-01 (health) |
| CAP-016 | External Connectivity | WP-05 |
| CAP-017 | Adapter Framework | WP-05 |
| CAP-021 | Deployment Automation | WP-08 |
| CAP-022 | Release Management | WP-08 |
| CAP-024 | Data Access | WP-02 |
| CAP-025 | Endpoint Security | WP-03, WP-04 |
| CAP-026 | Authentication Services | WP-04 |
| CAP-027 | Integration Security | WP-05 |
| CAP-028 | Background Processing | WP-06 |
| CAP-029 | Notification Management | WP-07 |
| CAP-030 | Service Deployment | WP-08 |

4.3 Authority → WP Mapping

| Authority | Name | Mapped WPs |
| --- | --- | --- |
| AUTH-002 | Service Framework Authority | WP-01 |
| AUTH-003 | Data Architecture Authority | WP-02 |
| AUTH-004 | API Design Authority | WP-03 |
| AUTH-006 | Service Lifecycle Authority | WP-01 |
| AUTH-007 | Data Integrity Authority | WP-02 |
| AUTH-011 | Security Policy Authority | WP-04 |
| AUTH-012 | API Gateway Authority | WP-03 |
| AUTH-013 | Access Control Authority | WP-04 |
| AUTH-014 | Identity Authority | WP-04 |
| AUTH-015 | Database Operations Authority | WP-02 |
| AUTH-018 | Integration Architecture Authority | WP-05 |
| AUTH-019 | External Service Authority | WP-05 |
| AUTH-022 | Deployment Authority | WP-08 |
| AUTH-023 | Release Authority | WP-08 |
| AUTH-024 | Runtime Operations Authority | WP-01 |
| AUTH-025 | Endpoint Management Authority | WP-03 |
| AUTH-026 | Authentication Service Authority | WP-04 |
| AUTH-027 | Integration Security Authority | WP-05 |
| AUTH-028 | Job Processing Authority | WP-06 |
| AUTH-029 | Queue Management Authority | WP-06 |
| AUTH-030 | Notification Authority | WP-07 |
| AUTH-031 | Message Delivery Authority | WP-07 |
| AUTH-032 | Environment Deployment Authority | WP-08 |

4.4 Traceability Summary

Total Capabilities Mapped: 24 CAPs across 8 WPs

Total Authorities Mapped: 23 AUTHs across 8 WPs

Civilizational Objectives Covered: 6/6 (100%)

Traceability Completeness: 100% — Every WP has ≥2 Atlas references

════════════════════════════════════════════════════════════

# DELIVERABLE 5: ACCEPTANCE CRITERIA

This deliverable consolidates all acceptance criteria across EP-02 into a program-level view. Criteria are organized by WP with priority classification, then aggregated into program-level gates.

5.1 WP Acceptance Criteria Summary

| WP | Name | AC Count | Priority | Key Coverage Areas |
| --- | --- | --- | --- | --- |
| WP-01 | Runtime Environment | 9 | CRITICAL | Process lifecycle, resource quotas, sandbox, bootstrap, health, degradation, telemetry, coverage |
| WP-02 | Data Service Layer | 9 | CRITICAL | CRUD, validation, query optimization, caching, transactions, audit, batch, slow query, coverage |
| WP-03 | Service Endpoints | 10 | HIGH | REST codes, GraphQL timing, mutations, WebSocket, DTOs, versioning, rate limiting, OpenAPI, RBAC, contracts |
| WP-04 | Security Services | 10 | HIGH | JWT lifecycle, tamper rejection, permissions, API keys, audit log, key rotation, anomaly detection, sessions, hot-reload, incidents |
| WP-05 | External Integration | 8 | MEDIUM | HTTP retries, circuit breaker, webhook verification, file formats, legacy adapters, health monitoring, audit logging, mock tests |
| WP-06 | Background Jobs | 8 | MEDIUM | FIFO processing, scheduler accuracy, concurrency, retry backoff, dead letter, monitoring, priority, idempotency |
| WP-07 | Notification Service | 9 | MEDIUM | Multi-channel routing, email templates, SMS receipts, push timing, in-app real-time, template versioning, preferences, tracking, rate limiting |
| WP-08 | CI/CD & Deployment | 9 | HIGH | Pipeline builds, blue-green, feature flags, environment promotion, smoke tests, rollback timing, audit trail, canary, pipeline timing |

5.2 Program-Level Acceptance Gates

| Gate | Criterion 1 | Criterion 2 | Criterion 3 | Criterion 4 |
| --- | --- | --- | --- | --- |
| GATE A: Technical Quality | All unit + integration tests PASS | Code coverage ≥80% | Zero critical security findings | Performance benchmarks within 110% of targets |
| GATE B: Functional Completeness | All 8 WPs COMPLETE with signed WP Completion Reports | All 72 acceptance criteria PASS (9+10+10+10+8+8+9+9) | No acceptance criterion marked FAIL without documented exception | Contract tests pass for all API endpoints |
| GATE C: Operational Readiness | Blue-green deployment verified with zero downtime | Rollback completes in <3 minutes | Monitoring captures all critical metrics | Alerting triggers correctly on simulated failures |
| GATE D: Security Compliance | OWASP Top 10 mitigations verified | All auth flows tested (success/failure/edge cases) | Security audit log contains all access decisions | Key rotation completes without service interruption |
| GATE E: EP-03 Readiness | All 8 EP-02→EP-03 transition dependencies satisfied | API contracts documented and versioned | Integration points tested with mock EP-03 consumers | Documentation complete for EP-03 onboarding |

5.3 Acceptance Criteria Statistics

Total Acceptance Criteria: 72 across 8 WPs

CRITICAL WP Priority: 2 WPs (WP-01, WP-02)

HIGH WP Priority: 3 WPs (WP-03, WP-04, WP-08)

MEDIUM WP Priority: 3 WPs (WP-05, WP-06, WP-07)

Program Gates: 5 (A: Technical, B: Functional, C: Operational, D: Security, E: EP-03 Readiness)

Minimum Pass Rate: 100% — No FAIL accepted for EP-02 COMPLETE status

════════════════════════════════════════════════════════════

# DELIVERABLE 6: EVIDENCE REQUIREMENTS

This deliverable defines the complete evidence framework for EP-02. It specifies evidence types, storage requirements, naming conventions, and the evidence registry structure. Every WP has specific evidence items defined in Deliverable 2 — this section provides the overarching framework and aggregation.

6.1 Evidence Type Taxonomy

| Type | Description | Storage Format | Priority |
| --- | --- | --- | --- |
| CODE | Source code, configuration files, build scripts | Git repository with tagged commits | CRITICAL |
| TEST | Unit test results, integration test results, contract test results | Test report in standard format (JUnit/XML) | CRITICAL |
| COVERAGE | Code coverage reports with line/branch/method metrics | HTML/XML coverage report (≥80%) | CRITICAL |
| PERF | Performance benchmark results, load test results, timing measurements | Benchmark report with before/after comparison | HIGH |
| SEC | Security scan results, penetration test results, vulnerability assessments | Scan report (SAST/DAST) with zero critical findings | CRITICAL |
| DOC | Architecture docs, API docs, runbooks, operational procedures | Markdown/PDF in version-controlled docs directory | HIGH |
| REVIEW | Code review records, architecture review sign-offs, Kimi approval records | Review comments + approval in tracking system | CRITICAL |
| AUDIT | Audit logs, access logs, change logs | Structured log files with correlation IDs | HIGH |
| SCREEN | Screenshots, dashboard captures, visualization exports | PNG/SVG with timestamp watermark | MEDIUM |
| ARCH | Architecture diagrams, data flow diagrams, deployment diagrams | Source (draw.io) + Rendered (PNG/SVG) | HIGH |

6.2 Evidence Registry Structure

EP-02_EVIDENCE_REGISTRY/
├── WP-01_Runtime_Environment/
│   ├── EV-01_Process_Lifecycle_Test/
│   ├── EV-02_Resource_Quota_Test/
│   ├── ... (9 evidence items per WP-01)
│   └── WP-01_Evidence_Index.md
├── WP-02_Data_Service_Layer/
│   ├── EV-01_CRUD_Test_Matrix/
│   ├── EV-02_Validation_Test/
│   ├── ... (9 evidence items per WP-02)
│   └── WP-02_Evidence_Index.md
├── WP-03_Service_Endpoints/
│   ├── ... (10 evidence items)
│   └── WP-03_Evidence_Index.md
├── WP-04_Security_Services/
│   ├── ... (10 evidence items)
│   └── WP-04_Evidence_Index.md
├── WP-05_External_Integration/
│   ├── ... (8 evidence items)
│   └── WP-05_Evidence_Index.md
├── WP-06_Background_Jobs/
│   ├── ... (8 evidence items)
│   └── WP-06_Evidence_Index.md
├── WP-07_Notification_Service/
│   ├── ... (9 evidence items)
│   └── WP-07_Evidence_Index.md
├── WP-08_CICD_Deployment/
│   ├── ... (9 evidence items)
│   └── WP-08_Evidence_Index.md
├── Program_Level/
│   ├── GATE-A_Technical_Quality_Report/
│   ├── GATE-B_Functional_Completeness_Report/
│   ├── GATE-C_Operational_Readiness_Report/
│   ├── GATE-D_Security_Compliance_Report/
│   ├── GATE-E_EP03_Readiness_Report/
│   └── EP-02_Master_Evidence_Index.md
└── README.md

6.3 Evidence Statistics

Total Evidence Items: 72 items (9+9+10+10+8+8+9+9)

Evidence Types Required: CODE, TEST, COVERAGE, PERF, SEC, DOC, REVIEW, AUDIT, SCREEN, ARCH

Minimum Coverage Threshold: 80% line coverage, 70% branch coverage

Security Requirement: Zero critical findings from SAST scan

Naming Convention: EV-[WP-NN]-[NNN]_[Short_Description]/

════════════════════════════════════════════════════════════

# DELIVERABLE 7: CRITICAL PATH ANALYSIS

This deliverable identifies the critical path through EP-02 — the longest dependency chain that determines the minimum possible duration. Any delay on the critical path delays EP-02 completion and EP-03 readiness.

7.1 Critical Path Definition

CRITICAL PATH:

WP-01 (2.5w) → WP-02 (2.5w) → WP-04 (2w) → WP-08 (1.5w)

= 8.5 weeks minimum (critical path only)

7.2 Critical Path Rationale

WP-01 (Runtime Environment): Foundation for ALL EP-02 WPs. No other WP can start without runtime hosting.

WP-02 (Data Service Layer): Sequential after WP-01. Provides data access for WP-04 security services and WP-08 deployment verification.

WP-04 (Security Services): Sequential after WP-02. Security services must be operational before WP-08 deployment verification can test secured endpoints.

WP-08 (CI/CD & Deployment): Final WP. Depends on ALL prior WPs being complete (services to deploy).

7.3 Non-Critical Path Branches

| Branch | Path | Timing | Duration | Float |
| --- | --- | --- | --- | --- |
| BRANCH A | WP-01 → WP-03 (Endpoints) | PARALLEL with WP-02 after WP-01 | 2-3 weeks | Float: 0.5-1 week |
| BRANCH B | WP-01 → WP-05 (Integration) | PARALLEL after WP-03/WP-04 | 2 weeks | Float: 1-2 weeks |
| BRANCH C | WP-01 → WP-06 (Jobs) | PARALLEL after WP-02 | 1-2 weeks | Float: 1-2 weeks |
| BRANCH D | WP-01 → WP-07 (Notifications) | PARALLEL after WP-03 | 1-2 weeks | Float: 1-2 weeks |

7.4 Critical Path Impact Analysis

WP-01 delay: Delays ALL other WPs. Every week of WP-01 delay adds one week to EP-02 completion.

WP-02 delay: Delays WP-04 and WP-06 (which depend on WP-02). WP-03 can still proceed in parallel.

WP-04 delay: Delays WP-08 directly. WP-05, WP-06, WP-07 can still complete but WP-08 is blocked.

WP-08 delay: No downstream EP-02 impact (it's the final WP), but delays EP-03 readiness gate.

════════════════════════════════════════════════════════════

# DELIVERABLE 8: PARALLELIZATION OPPORTUNITIES — 4 EXECUTION PATHS

This deliverable identifies four distinct execution paths through EP-02, ordered from most conservative to most aggressive. The Founder must authorize the execution path before EP-02 issuance. Default: PARALLEL PATH.

## PATH 1: SEQUENTIAL PATH (Conservative — Maximum Safety)

Description: Execute one WP at a time in strict dependency order. Zero parallelization. Maximum focus per WP.

Execution Order: WP-01 → WP-02 → WP-03 → WP-04 → WP-05 → WP-06 → WP-07 → WP-08

Estimated Duration: 14-16 weeks

Team Requirement: 1 execution owner (Husam), 100% focus on one WP at a time

Risk Profile: LOW — No context switching, no integration conflicts during execution

Trade-off: Longest timeline but highest quality per WP and lowest cognitive load

Recommended When: Husam working alone, high complexity WPs, high quality requirement

## PATH 2: PARALLEL PATH (Balanced — Recommended Default)

Description: Execute WPs in parallel where dependencies permit. Phase-based execution with parallel streams.

Phase 1: WP-01 (sequential foundation)

Phase 2: WP-02 + WP-03 (parallel after WP-01)

Phase 3: WP-04 + WP-05 + WP-06 + WP-07 (parallel after Phase 2)

Phase 4: WP-08 (sequential final)

Estimated Duration: 10-12 weeks

Team Requirement: 1-2 execution owners, context switching between 2 parallel WPs in Phase 2, 4 in Phase 3

Risk Profile: MEDIUM — Context switching overhead, integration timing between parallel WPs

Trade-off: 30% faster than sequential with manageable complexity increase

Recommended When: Default recommendation. Balanced speed and safety.

## PATH 3: FAST-TRACK PATH (Aggressive — Expedited Delivery)

Description: Maximize parallelization with overlap. Start WP-03 before WP-02 completes (staged integration). Overlap Phase 2 and Phase 3.

Phase 1: WP-01 (sequential foundation)

Phase 2: WP-02 + WP-03 (parallel, with WP-03 starting when WP-02 70% complete)

Phase 3: WP-04 + WP-05 + WP-06 + WP-07 (all parallel, starting as early as dependencies allow)

Phase 4: WP-08 (overlaps with Phase 3 final integration)

Estimated Duration: 8-10 weeks

Team Requirement: 2+ execution owners, heavy context switching, strong coordination required

Risk Profile: HIGH — Integration conflicts likely, technical debt accumulation, quality risk without strong testing

Trade-off: 40% faster than sequential but requires strong discipline and automated testing

Recommended When: EP-01 completed ahead of schedule, strong testing infrastructure (WP-09 from EP-01), team expansion

## PATH 4: MAXIMUM THROUGHPUT PATH (Maximum Aggressive — Parallel Everything Possible)

Description: Execute ALL non-dependent WPs in parallel from the earliest possible moment. Maximum density, minimum calendar time.

Week 1-2.5:  WP-01 (sequential foundation)

Week 2.5-5:   WP-02 + WP-03 (parallel)

Week 5-7:     WP-04 + WP-05 + WP-06 + WP-07 (4-WAY PARALLEL)

Week 7-8.5:   WP-08 (sequential final with parallel integration testing)

Estimated Duration: 8-10 weeks (calendar time, same as Fast-Track but higher resource utilization)

Team Requirement: 3+ execution owners, dedicated integration lead, full automation

Risk Profile: VERY HIGH — Maximum context switching, high integration conflict probability, requires dedicated integration management

Trade-off: Minimum calendar time but maximum resource consumption and coordination overhead

Recommended When: Multiple execution owners available, EP-01 testing infrastructure proven, dedicated integration management, hard deadline constraint

8.5 Path Comparison Summary

| Path | Duration | Team Size | Risk | Best For |
| --- | --- | --- | --- | --- |
| 1. Sequential | 14-16 weeks | 1 | LOW | Solo execution, maximum quality |
| 2. Parallel (DEFAULT) | 10-12 weeks | 1-2 | MEDIUM | Balanced speed/safety |
| 3. Fast-Track | 8-10 weeks | 2+ | HIGH | Aggressive timeline, strong infra |
| 4. Max Throughput | 8-10 weeks | 3+ | VERY HIGH | Hard deadline, full team |

8.6 Path Selection Authority

Default Path: PATH 2: PARALLEL (unless Founder specifies otherwise)

Selection Authority: Founder — Path selection must be specified in ONX-EP02-2026-001 Issuance Document

Path Change During Execution: Requires CCR-Type-C (Execution Realignment) with Founder approval

════════════════════════════════════════════════════════════

# DELIVERABLE 9: RUNTIME REALIZATION PLAN

This deliverable maps the Atlas V5.0 Runtime Definitions (Phase 4) to EP-02 Work Packages. Each runtime defined in Atlas must be realized by a specific WP. This ensures constitutional compliance: every runtime has a responsible WP, every WP realizes at least one Atlas runtime.

9.1 Runtime → WP Realization Mapping

| Runtime ID | Runtime Name | Capability | WP | WP Name |
| --- | --- | --- | --- | --- |
| RT-001 | Core Runtime Host | CAP-001 | WP-01 | Runtime Environment Setup |
| RT-002 | Service Container | CAP-001 | WP-01 | Runtime Environment Setup |
| RT-003 | DI Resolution Engine | CAP-001 | WP-01 | Runtime Environment Setup |
| RT-005 | Resource Manager | CAP-001 | WP-01 | Runtime Environment Setup |
| RT-006 | Sandbox Context | CAP-001 | WP-01 | Runtime Environment Setup |
| RT-007 | Health Monitor | CAP-015 | WP-01 | Runtime Environment Setup |
| RT-008 | Telemetry Collector | CAP-007 | WP-01 | Runtime Environment Setup |
| RT-010 | CRUD Service Base | CAP-005 | WP-02 | Data Service Layer |
| RT-011 | Query Optimizer | CAP-005 | WP-02 | Data Service Layer |
| RT-012 | Cache Manager | CAP-005 | WP-02 | Data Service Layer |
| RT-013 | Transaction Coordinator | CAP-006 | WP-02 | Data Service Layer |
| RT-014 | Data Validator | CAP-006 | WP-02 | Data Service Layer |
| RT-015 | Audit Logger (Data) | CAP-006 | WP-02 | Data Service Layer |
| RT-020 | REST Controller | CAP-009 | WP-03 | Service Endpoints |
| RT-021 | GraphQL Resolver | CAP-009 | WP-03 | Service Endpoints |
| RT-022 | WebSocket Handler | CAP-011 | WP-03 | Service Endpoints |
| RT-023 | Request Mapper | CAP-009 | WP-03 | Service Endpoints |
| RT-025 | JWT Token Service | CAP-012 | WP-04 | Security Services |
| RT-026 | Permission Evaluator | CAP-013 | WP-04 | Security Services |
| RT-027 | API Key Manager | CAP-012 | WP-04 | Security Services |
| RT-028 | Security Audit Logger | CAP-004 | WP-04 | Security Services |
| RT-029 | Session Manager | CAP-012 | WP-04 | Security Services |
| RT-030 | Encryption Key Manager | CAP-004 | WP-04 | Security Services |
| RT-035 | External HTTP Client | CAP-016 | WP-05 | External Integration |
| RT-036 | Webhook Processor | CAP-016 | WP-05 | External Integration |
| RT-037 | File Import/Export | CAP-016 | WP-05 | External Integration |
| RT-038 | Legacy Adapter Host | CAP-017 | WP-05 | External Integration |
| RT-040 | Job Queue Manager | CAP-028 | WP-06 | Background Jobs |
| RT-041 | Job Scheduler | CAP-028 | WP-06 | Background Jobs |
| RT-042 | Worker Pool | CAP-028 | WP-06 | Background Jobs |
| RT-043 | Retry Engine | CAP-028 | WP-06 | Background Jobs |
| RT-044 | Dead Letter Handler | CAP-028 | WP-06 | Background Jobs |
| RT-045 | Notification Dispatcher | CAP-029 | WP-07 | Notification Service |
| RT-046 | Email Service | CAP-029 | WP-07 | Notification Service |
| RT-047 | SMS Gateway | CAP-029 | WP-07 | Notification Service |
| RT-048 | Push Notification Service | CAP-029 | WP-07 | Notification Service |
| RT-050 | Deployment Pipeline | CAP-021 | WP-08 | CI/CD & Deployment |
| RT-051 | Blue-Green Deployer | CAP-021 | WP-08 | CI/CD & Deployment |
| RT-052 | Rollback Controller | CAP-022 | WP-08 | CI/CD & Deployment |
| RT-053 | Canary Deployer | CAP-022 | WP-08 | CI/CD & Deployment |
| RT-054 | Feature Flag Manager | CAP-014 | WP-08 | CI/CD & Deployment |
| RT-055 | Environment Promoter | CAP-014 | WP-08 | CI/CD & Deployment |

9.2 Runtime Realization Statistics

Total EP-02 Runtimes: 37 runtimes mapped (out of 56 total Atlas runtimes)

WP-01 Runtimes: 8 runtimes (RT-001 through RT-008)

WP-02 Runtimes: 6 runtimes (RT-010 through RT-015)

WP-03 Runtimes: 5 runtimes (RT-020 through RT-023)

WP-04 Runtimes: 6 runtimes (RT-025 through RT-030)

WP-05 Runtimes: 4 runtimes (RT-035 through RT-038)

WP-06 Runtimes: 5 runtimes (RT-040 through RT-044)

WP-07 Runtimes: 4 runtimes (RT-045 through RT-048)

WP-08 Runtimes: 6 runtimes (RT-050 through RT-055)

Unmapped Runtimes: 19 runtimes (EP-01: 14, EP-03: 3, EP-04: 1, EP-05: 1)

Realization Completeness: 100% — All EP-02 scoped runtimes have responsible WP

════════════════════════════════════════════════════════════

# DELIVERABLE 10: EP-02 → EP-03 TRANSITION MAP

This deliverable defines the complete transition interface from EP-02 to EP-03. It specifies the deliverables EP-02 must produce for EP-03 consumption, the readiness gates EP-03 activation requires, and the contractual stability guarantees between the two programs.

10.1 EP-02 → EP-03 Transition Deliverables

| TD ID | Deliverable | Description | Source WP | Priority |
| --- | --- | --- | --- | --- |
| TD-01 | API Contract Specification | Complete OpenAPI 3.0 + GraphQL schema for all EP-02 endpoints | WP-03 | CRITICAL |
| TD-02 | Authentication Integration Guide | Documentation for how EP-03 frontend integrates with EP-02 auth services | WP-04 | CRITICAL |
| TD-03 | Service Health Endpoints | Liveness/readiness probe endpoints for EP-03 to verify EP-02 availability | WP-01 | HIGH |
| TD-04 | Error Response Standard | Standardized error format documentation for all EP-02 services | WP-03 | HIGH |
| TD-05 | Data Model Documentation | Entity relationship diagram + field descriptions for all API-exposed models | WP-02 | HIGH |
| TD-06 | Rate Limiting Configuration | Documented rate limits per endpoint category for EP-03 to respect | WP-03 | MEDIUM |
| TD-07 | Webhook Subscription API | API for EP-03 to subscribe to real-time events from EP-02 services | WP-05 | MEDIUM |
| TD-08 | Notification Channel Registration | API for EP-03 to register notification channels (in-app, push) | WP-07 | MEDIUM |
| TD-09 | Environment Configuration Template | Environment-specific config templates for EP-03 deployment | WP-08 | HIGH |
| TD-10 | Security Headers & CORS Policy | Documented CORS configuration, required security headers, CSP policy | WP-04 | CRITICAL |
| TD-11 | Deployment Dependency Map | Documentation of EP-02 service startup order and health check timing | WP-08 | HIGH |
| TD-12 | Observability Integration Guide | How EP-03 frontend errors integrate with EP-02 observability | WP-01 | MEDIUM |

10.2 EP-03 Readiness Gates

| Gate ID | Name | Criterion | Depends On |
| --- | --- | --- | --- |
| G-EP03-01 | API Stability | All EP-02 API contracts frozen (versioned). No breaking changes without CCR. | TD-01 |
| G-EP03-02 | Auth Integration Verified | EP-03 team has successfully authenticated against EP-02 auth service in staging | TD-02 |
| G-EP03-03 | Health Probes Active | All EP-02 services report healthy in staging environment for 48+ hours | TD-03 |
| G-EP03-04 | Error Handling Documented | EP-03 team has error handling guide for all EP-02 error responses | TD-04 |
| G-EP03-05 | Data Model Understood | EP-03 team has reviewed and acknowledged data model documentation | TD-05 |
| G-EP03-06 | Rate Limits Respected | EP-03 implementation respects documented rate limits (verified by test) | TD-06 |
| G-EP03-07 | WebSocket Events Working | Real-time event subscription from EP-02 to EP-03 verified end-to-end | TD-07 |
| G-EP03-08 | Deployment Coordination | EP-03 deployment process coordinates with EP-02 deployment (order, timing) | TD-11 |

10.3 Contract Stability Guarantee

EP-02 commits to API contract stability for the duration of EP-03 execution. Breaking changes to EP-02 APIs after EP-03 start require a CCR-Type-C with minimum 2-week notice. EP-02 shall maintain backward compatibility through API versioning (v1, v2) for at least one full EP cycle.

API versions SHALL be maintained for minimum 90 days after new version release

Deprecated endpoints SHALL return warning headers with sunset dates

Breaking changes SHALL be announced via CCR-Type-C minimum 14 days before deployment

Non-breaking additive changes (new fields, new endpoints) do not require CCR

EP-03 SHALL specify target API version in all requests (default: v1)

10.4 EP-03 Activation Sequence

STEP 1: EP-02 WP-08 COMPLETE — All EP-02 services deployed and operational

STEP 2: EP-02 Final Verdict: COMPLETE — Kimi signs off, Founder acknowledges

STEP 3: Transition Deliverables (TD-01 through TD-12) published to EP-03 workspace

STEP 4: EP-03 Readiness Gates (G-EP03-01 through G-EP03-08) verification begins

STEP 5: Kimi verifies all 8 gates PASS within 72 hours

STEP 6: Founder issues ONX-EP03-2026-001 (EP-03 Authorization)

STEP 7: ONX-EHP-2026-003 (EP-03 Handover Package) generated from EP-03 Pre-Issuance Package

STEP 8: Husam receives EP-03 package and begins EP-03 execution

STEP 9: EP-02 transitions to MAINTENANCE mode — bug fixes and contract stability only

════════════════════════════════════════════════════════════

# APPENDIX A: DOCUMENT HISTORY

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-06-20 | Kimi | Complete 10-deliverable pre-issuance package — PRE-ISSUANCE state |

# APPENDIX B: REFERENCE DOCUMENTS

ONX-ATLAS-V5.0: ONX Atlas V5.0 Baseline Artifact (Frozen)

ATRP-2026-001: Atlas V5.0 Realization Program Directive

ONX-EHP-2026-001: EP-01 Execution Handover Package

ONX-EP01-2026-001: EP-01 Execution Issuance Confirmation

ONX-EP02-PREP-2026-001: This document — EP-02 Pre-Issuance Directive

ONX-BASELINE-FREEZE: Atlas V5.0 Baseline Freeze Document (ONX13-R5A)

ONX-VERDICT-D: Final Verdict D Certification Report

CAP-DNA-VOL-01-04: Capability DNA Cards (4 volumes, 56 cards)

AUTH-DNA-VOL-01-04: Authority DNA Cards (4 volumes, 89 cards)

ONX-REG-9B: Mandatory Registry Layer (16 registries, 515 records)

ONX-CFL-PH10: Constitutional Fitness Layer (12 domains, 23 simulations)

# APPENDIX C: ABBREVIATIONS & TERMS

ADAPT: Asset classification: Modify before reuse

ADR: Architecture Decision Record

ATRP: Atlas Realization Program

CAP: Capability (CAP-NNN format)

CCR: Constitutional Change Request

CD: Continuous Deployment

CI: Continuous Integration

CO: Civilizational Objective (CO-001 to CO-006)

CRUD: Create, Read, Update, Delete

DI: Dependency Injection

DTO: Data Transfer Object

EP: Execution Program (EP-01 to EP-05)

EV: Evidence item (EV-NN format)

IaC: Infrastructure as Code

JWT: JSON Web Token

KEEP: Asset classification: Use as-is

RBAC: Role-Based Access Control

REST: Representational State Transfer

RT: Runtime Definition (RT-NNN format)

SAST: Static Application Security Testing

TD: Transition Deliverable (TD-NN format)

WP: Work Package (WP-NN format)

# APPENDIX D: ISSUANCE ACTIVATION CHECKLIST

This checklist must be completed BEFORE EP-02 can transition from PRE-ISSUANCE to ISSUED status:

☐ EP-01 M-08 milestone CONFIRMED — EP-01 COMPLETE

☐ EP-01 Final Verdict: COMPLETE — Founder acknowledged

☐ Kimi verifies EP-02 Readiness Criteria (all 8 items) — SATISFIED

☐ Founder reviews this Pre-Issuance Package and approves

☐ Execution Path selected (Sequential/Parallel/Fast-Track/Max Throughput)

☐ ONX-EP02-2026-001 Issuance Document generated and signed

☐ ONX-EHP-2026-002 (EP-02 Handover Package) derived from this document

☐ Husam briefing session scheduled and completed

☐ Husam acknowledges receipt of ONX-EHP-2026-002

☐ EP-02 evidence registry initialized and ready

☐ All 12 Transition Deliverables (TD-01 to TD-12) prepared for EP-03

☐ Contract stability guarantee documented and acknowledged

╔══════════════════════════════════════════════════════════════════╗
║  EP-02 STATUS: PRE-ISSUANCE — READY FOR ISSUANCE BUT NOT ISSUED ║
║  BLOCKING CONDITION: EP-01 READINESS GATE (M-08)               ║
║  ALL 10 DELIVERABLES: COMPLETE                                  ║
║  EXECUTION PATHS: 4 DEFINED (Sequential/Parallel/Fast-Track/Max) ║
╚══════════════════════════════════════════════════════════════════╝

ONX Atlas Realization Program — EP-02 Pre-Issuance Package v1.0
Prepared by: Kimi (Atlas Custodian) | Authorized by: Mohammed Shaheen (Founder)
Date: 2026-06-20 | Classification: PRE-ISSUANCE