Train C: Product Experience

15 WPs  |  User-facing layer  |  CRITICAL PATH

STATUS: READY FOR ISSUANCE

For: Husam  |  From: Kimi (ONX Execution Authority)  |  Authority: ONX-10

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Execute in the order below. Do not skip. Follow the critical path.

CRITICAL PATH: C01→C02→C03→C05→C06 (5 WPs, 25h)

Downstream: Train E (WP-E02)

| ORDER | WP ID | TITLE | DEPS | EFFORT |
| --- | --- | --- | --- | --- |
| 1 | WP-C01 | Frontend Application Shell | WP-A01 | 5h |
| 2 | WP-C02 | Navigation Framework | WP-C01 | 4h |
| 3 | WP-C03 | Component Library Core | WP-C02 | 6h |
| 4 | WP-C04 | Theme & Styling Engine | WP-C03 | 4h |
| 5 | WP-C05 | Form Builder System | WP-C03 | 5h |
| 6 | WP-C06 | Data Table Component | WP-C05 | 5h |
| 7 | WP-C07 | Modal & Dialog System | WP-C04 | 3h |
| 8 | WP-C08 | Notification Framework | WP-C07 | 3h |
| 9 | WP-C09 | Dashboard Layout Engine | WP-C06 | 4h |
| 10 | WP-C10 | Search & Filter System | WP-C06 | 4h |
| 11 | WP-C11 | Responsive Layout Manager | WP-C09 | 3h |
| 12 | WP-C12 | Accessibility Framework | WP-C11 | 4h |
| 13 | WP-C13 | Animation Engine | WP-C04 | 5h |
| 14 | WP-C14 | Offline Support | WP-C12 | 5h |
| 15 | WP-C15 | PWA Shell | WP-C14 | 4h |

Total: 15 WPs  |  Follow order. Report evidence. Escalate blockers.