WAVE-1: OPERATIONAL EXECUTION PACKAGE

Trains A+B+C+D+E  |  100 WPs  |  Jun-Oct 2026

STATUS: READY FOR ISSUANCE

For: Husam  |  From: Kimi (ONX Execution Authority)  |  Authority: ONX-10

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Wave-1 establishes the complete foundation. All core systems operational. Product shell functional. Infrastructure deployed. Analytics running.

## TRAIN SUMMARY

| TRAIN | WPs | PRIORITY | TIMEFRAME | NOTE |
| --- | --- | --- | --- | --- |
| Train A: Foundation | 15 WPs | CRITICAL | Jun-Jul 2026 | All other trains depend on this |
| Train B: Runtime | 15 WPs | CRITICAL | Jul-Aug 2026 | Execution environment |
| Train C: Product | 15 WPs | CRITICAL | Jul-Aug 2026 | User-facing layer |
| Train D: Operations | 15 WPs | CRITICAL | Aug-Sep 2026 | Infrastructure + CI/CD |
| Train E: Intelligence | 15 WPs | HIGH | Sep-Oct 2026 | Analytics + ML |

## CROSS-TRAIN DEPENDENCIES

→ Train A → Train B: WP-A02 enables WP-B01 (Framework → Runtime)

→ Train A → Train C: WP-A01 enables WP-C01 (Architecture → Product Shell)

→ Train A → Train D: WP-A03 enables WP-D01 (Config → Infrastructure)

→ Train A → Train E: WP-A06 enables WP-E01 (State Mgmt → Analytics)

→ Train B → Train E: WP-B05 enables WP-E03 (Async → Data Pipeline)

→ Train C → Train E: WP-C06 enables WP-E02 (Data Tables → Reporting)

→ Train D → Train B: WP-D01 enables WP-B01 (Infra → Runtime Deploy)

→ Train D → Train C: WP-D02 enables WP-C01 (CI/CD → Frontend Deploy)

## MILESTONES

| MILESTONE | NAME | CRITERIA | TARGET |
| --- | --- | --- | --- |
| M1 | Foundation Complete | Train A critical path done | Jul 15 |
| M2 | Runtime Operational | Train B core running | Aug 15 |
| M3 | Product Shell Live | Train C deployed | Aug 31 |
| M4 | Infrastructure Stable | Train D production-ready | Sep 15 |
| M5 | Analytics Running | Train E processing | Sep 30 |
| M6 | Wave-1 Exit | All exit criteria met | Oct 15 |

## EXIT CRITERIA

✓ All 100 WPs completed with 9-point gate pass

✓ Train A: Bootstrap sequence operational

✓ Train B: Runtime stable at 1000 ops/s

✓ Train C: Frontend renders + navigation works

✓ Train D: Infrastructure deployed + CI/CD green

✓ Train E: Analytics collecting + reports generating

✓ Cross-train integration tests passing

✓ End-to-end smoke test successful

✓ Founder approval for Wave-2